## jose demasi
Jose Demasi
Open Tasks
Name | Subitems | Person | Status | Priority | Due Date | Date | Item ID (auto generated)
US Chimney Supply Website |  | Jose Demasi | Received |  | 2026-01-20 |  | 10731479120
A1 Chimney Website | Create Page for each location,Create Link For Survey - Reviews (update Shoval once done),Booking link for return clients,Change Content Per Haim,Add Socials For each subdomain,Maintenance Program Changes,Photo & Design Changes,Franchise Page - Main Page (Ask Shoval) | Bar Ohayon | Received |  |  |  | 9183424935
Subitems | Name | Owner | Category | Status | Date | Item ID (auto generated)
| Create Page for each location |  |  |  |  | 9250122411
| Create Link For Survey - Reviews (update Shoval once done) |  |  |  |  | 9183434667
| Booking link for return clients |  |  |  |  | 9183429078
| Change Content Per Haim |  |  |  |  | 9183440850
| Add Socials For each subdomain |  |  |  |  | 9183443047
| Maintenance Program Changes |  |  |  |  | 9183451628
| Photo & Design Changes |  |  |  |  | 9183453905
| Franchise Page - Main Page (Ask Shoval) |  |  |  |  | 10648481955
A1 Chimney PPC |  |  | Received |  |  |  | 10648525747
BBB Accredited Setup |  |  | Received |  |  |  | 10608020593
A1 Roofing Website - Texas |  | Jose Demasi | Received |  |  |  | 9581883400
Websites Changes: A1 Chimney Sweep ¦ Ace Fireplace |  |  | Received |  |  |  | 10673287159
Ring Central Training Bar |  | Jose Demasi | Received |  |  |  | 10791185082
Marketing Projects | Build Facebook Ads Campgain,Text Marketing,SMS Marketing |  | Received |  |  |  | 10022110706
Subitems | Name | Owner | Category | Status | Date | Item ID (auto generated)
| Build Facebook Ads Campgain | Bar Ohayon |  |  |  | 10022111336
| Text Marketing |  |  |  |  | 10582606999
| SMS Marketing |  |  |  |  | 10843390309
A1 Tools | Inventory Solution & Supply,Build AI Dispatch Data & Calls Simulation.,Monday CRM Dispatch Report,Workiz Bookings & Distance Feature,Local Services Massage Bot,Tech AI Summarizing,Monday Emails Integration,LS Ads Booked / Not Booked Bot,Technician Tracking,Build Training Course for other Rules.,Dispatch Course Upgrade - Add Introduction - New Guidelines. |  | Received |  | 2026-02-28 09:00 |  | 10648026199
Subitems | Name | Owner | Category | Status | Date | Item ID (auto generated)
| Inventory Solution & Supply | Jose Demasi |  | Working on it |  | 10074424134
| Build AI Dispatch Data & Calls Simulation. |  |  | Received |  | 10607946517
| Monday CRM Dispatch Report |  |  | Received |  | 10648095845
| Workiz Bookings & Distance Feature |  |  | Received |  | 10648112845
| Local Services Massage Bot |  |  | Received |  | 10650506476
| Tech AI Summarizing |  |  | Received |  | 10650512661
| Monday Emails Integration |  |  | Received |  | 10650509375
| LS Ads Booked / Not Booked Bot |  |  | Received |  | 10650515072
| Technician Tracking |  |  | Received |  | 10763079924
| Build Training Course for other Rules. |  |  | Stuck |  | 10607940617
| Dispatch Course Upgrade - Add Introduction - New Guidelines. |  |  | Done |  | 10607959768
2026-01-20 to 2026-02-28
Recurring Tasks
Name | Subitems | Person | Status | Priority | Due Date | Date | Item ID (auto generated)
Check All Lines & Numbers |  | Jose Demasi | Stuck |  |  |  | 10807636318
Completed Tasks
Name | Subitems | Person | Status | Priority | Due Date | Date | Item ID (auto generated)
Speedy Garage Door Repair |  | Jose Demasi | Done |  |  |  | 9302883853
Before & After project Rotem | Refractory Panel Replacement,Flashing Repair,Chase cover replacement,Stainless steel liner installation,Smoke chamber parging,Crown Replacement,Custom Cap Replacement,Cricket installation,Spark arrestor replacement,Firebox Remodeling,Gas Logs Set Installation,Chimney rebuild,Flashing replacement |  | Done |  |  |  | 9896301106
Subitems | Name | Owner | Category | Status | Date | Item ID (auto generated)
| Refractory Panel Replacement |  |  |  |  | 9896303071
| Flashing Repair |  |  |  |  | 9896304054
| Chase cover replacement |  |  |  |  | 9896304838
| Stainless steel liner installation |  |  |  |  | 9906256376
| Smoke chamber parging |  |  |  |  | 9917063148
| Crown Replacement |  |  |  |  | 9924984809
| Custom Cap Replacement |  |  |  |  | 9924995942
| Cricket installation |  |  |  |  | 9933136211
| Spark arrestor replacement |  |  |  |  | 9978011820
| Firebox Remodeling |  |  |  |  | 10000570144
| Gas Logs Set Installation |  |  |  |  | 10025384956
| Chimney rebuild |  |  |  |  | 10066941186
| Flashing replacement |  |  |  |  | 18161319793
Create Address Pages |  | Jose Demasi | Done |  |  |  | 9614490749
Air 75 |  | Jose Demasi | Done |  |  |  | 9129391380
US Garage Repair |  | Jose Demasi | Done |  |  |  | 9126417679
Premier Garage Repair |  | Jose Demasi | Done |  |  |  | 9203671354
Air 75 Car Wrap Design |  | Jose Demasi | Done |  |  |  | 9249455605
US Garage Doors | Change the main domain to general (no Connecticut),Change the phone number,Remove anywhere that says 24/7 | Jose Demasi | Done |  |  |  | 9408333800
Subitems | Name | Owner | Category | Status | Date | Item ID (auto generated)
| Change the main domain to general (no Connecticut) |  |  |  |  | 9408338537
| Change the phone number |  |  |  |  | 9408339796
| Remove anywhere that says 24/7 |  |  |  |  | 9408345307
A1 Garage Door Repair |  | Jose Demasi | Done |  |  |  | 9345240830
Add address to garage door websites |  | Jose Demasi | Done |  |  |  | 9389861407
Change header for us garage door |  | Jose Demasi | Done |  |  |  | 9485128621
Hours of operation |  | Jose Demasi | Done |  |  |  | 9495288839
TopUp Roofing Website |  | Jose Demasi | Done |  |  |  | 9244919012
TopUp Roofing - Phone Number |  | Jose Demasi | Done |  |  |  | 9518086816
Need to fix it asap |  | Jose Demasi | Done |  |  |  | 9524231798
A1 Chimney - Indiana |  | Jose Demasi | Done |  |  |  | 9518112414
A1 Chimney - Maryland |  | Jose Demasi | Done |  |  |  | 9541810369
A1 Chimney - Virginia |  | Jose Demasi | Done |  |  |  | 9541814792
Duplicate A1 Garage Door Website |  | Jose Demasi | Done |  |  |  | 9564455411
Website - Our Work Replacement | Standard Cap Replacement,Chase Cover Replacement,Custom Cap Replacement,Stainless steel liner installation,Siding replacement,Flashing repair,Glass door installation,Insert replacement,Gas logs set installation,Crown replacement,Smoke chamber parging,Spark arrestor replacement,T_Top Replacement,Chimney Rebuild,Chimney Bricks Replacement,Woodstove installation,Refractory Panel Replacement,Stucco Coating,Firebox Remodeling,Tuck Pointing,Stucco Repair,Chimney Cleaning,Flue Resurfacing (HeatShield) |  | Done |  |  |  | 9193713777
Subitems | Name | Owner | Category | Status | Date | Item ID (auto generated)
| Standard Cap Replacement |  | Done |  |  | 9254935050
| Chase Cover Replacement |  | Done |  |  | 9254938856
| Custom Cap Replacement |  | Done |  |  | 9255378949
| Stainless steel liner installation |  | Done |  |  | 9255381492
| Siding replacement |  | Done |  |  | 9255381707
| Flashing repair |  | Done |  |  | 9255382152
| Glass door installation |  | Done |  |  | 9255382507
| Insert replacement |  | Done |  |  | 9255384043
| Gas logs set installation |  | Done |  |  | 9255386370
| Crown replacement |  | Done |  |  | 9255392012
| Smoke chamber parging |  | Done |  |  | 9255393227
| Spark arrestor replacement |  | Done |  |  | 9255417698
| T_Top Replacement |  | Done |  |  | 9255434877
| Chimney Rebuild |  | Done |  |  | 9255572858
| Chimney Bricks Replacement |  | Done |  |  | 9456913975
| Woodstove installation |  | Done |  |  | 9541362820
| Refractory Panel Replacement |  | Done |  |  | 9556725316
| Stucco Coating |  | Done |  |  | 9564830449
| Firebox Remodeling |  | Done |  |  | 9594277724
| Tuck Pointing |  | Done |  |  | 9594319366
| Stucco Repair |  | Done |  |  | 9594354331
| Chimney Cleaning |  | Done |  |  | 9594732238
| Flue Resurfacing (HeatShield) |  | Done |  |  | 9594832058
A1 Garage Doors - Changes |  | Jose Demasi | Done |  |  |  | 9592456572
Plugins Update |  | Jose Demasi | Done |  |  |  | 9596667235
CrestLine Home Website |  | Jose Demasi | Done |  |  |  | 9501038842
Fix issue ASAP |  | Jose Demasi | Done |  |  |  | 9643167365
Disable all auto updates for websites |  | Jose Demasi | Done |  |  |  | 9647159928
A1 Garage Doors - UPDATE |  | Jose Demasi | Done |  |  |  | 9655324872
Premier Garage Door Repair - Boston |  | Jose Demasi | Done |  |  |  | 9655323917
Sign |  | Jose Demasi | Done |  |  |  | 9657046470
Speedy Garage Doors - Boston |  | Jose Demasi | Done |  |  |  | 9655322381
US Garage Repair - Boston |  | Jose Demasi | Done |  |  |  | 9655320459
Watermarking |  | Jose Demasi | Done |  |  |  | 9655457790
Duplicate Cresline Home |  | Jose Demasi | Done |  |  |  | 9698913437
Dispatcher Final Exam |  | Jose Demasi | Done |  |  |  | 9807833735
Speedy Chimney Sweep Logo |  |  | Done |  |  |  | 9654590386
Before & After Project | Gas Logs Set Installation,Custom Cap Replacement,Siding replacement,Standard Cap Replacement,Damper Cap Replacement,Crown Replacement,Gas Line Installation,Chase Cover Replacement,Spark Arrestor Replacement,WoodStove Installation,Chimney Pipes Replacement,Trimming Replacement |  | Done |  |  |  | 9595093105
Subitems | Name | Owner | Category | Status | Date | Item ID (auto generated)
| Gas Logs Set Installation |  | Done |  |  | 9608218786
| Custom Cap Replacement |  | Done |  |  | 9608219248
| Siding replacement |  | Done |  |  | 9639662401
| Standard Cap Replacement |  | Done |  |  | 9640160139
| Damper Cap Replacement |  | Done |  |  | 9650394664
| Crown Replacement |  | Done |  |  | 9673466022
| Gas Line Installation |  | Done |  |  | 9709122385
| Chase Cover Replacement |  | Done |  |  | 9719730717
| Spark Arrestor Replacement |  | Done |  |  | 9719733268
| WoodStove Installation |  | Done |  |  | 9719735943
| Chimney Pipes Replacement |  | Done |  |  | 9719739140
| Trimming Replacement |  | Done |  |  | 9847308574
Summaries points of ''how to sell video'' |  | Jose Demasi | Done |  |  |  | 9771016945
Topics for Chapter 3 |  | Jose Demasi | Done |  |  |  | 9923393777
Duplicate A1 Chimney |  | Jose Demasi | Done |  |  |  | 10063754760
A1 Chimney Employee Page | Jose Demasi - Marketing Department Manager,Rodrigo Mena - Marketing & Creative Director,David Marinelli - Marketing Specialist,Erik Enson - General Manager,Eve Sarfati - HR Manager,Selena Gittner - Sales Executive Manager,Chris Huerta - Sales Executive Manager,Moshe Hai Zion - Lead Chimney Technician CSIA Certification: 12496 - X,Menahem Maamari - Lead Chimney Technician CSIA 12399 - x,Neorai Maamari - Lead Chimney Technician - CSIA 12487 - x,Rotem Hadad - Lead Chimney Technician - CSIA 12491 - x,Avihay Malka - Lead Chimney Technician CSIA Certification: 12496 - x,Netanel Mulokandov - Lead Chimney Technician CSIA Certification: 12489 - x,Tamir Alon - Lead Chimney Technician - 12397 - x,Nahman Melci - Chimney Technician - CSIA 12389 - x,Itzhak Swartz - Chimney Technician - CSIA 12398 - x,Michael Thompson - Chimney Technician - CSIA 12392 x,Ronald Rivera - Chimney Technician X,Akiva Meltzer - Chimney Technician x,Actors NJ - Bar will send,Darren Couch - Apprentice Chimney Technician - CSIA 12390 x,Pedro Saez - Masonery Specialist x,Darwin Sanchez - Masonery Specialist x,Emily Parker - Customer Experience Specialist,Jessica Coleman - Customer Experience Specialist,Hannah Brooks - Technician Supervisor,Rachel Monroe - Technician Supervisor,Ashley Plummer - Technician Supervisor,Megan Sullivan - Customer Service Representative,Lauren Mitchell - Customer Service Representative,Samantha Hayes - Customer Service Representative,Natalie Reed - Customer Service Representative,Daniella Burnes - Customer Service Representative,Santiago Lugo - Customer Service Representative,Sara Persad - Customer Service Representative | Shoval Ohayon | Done |  |  |  | 9203528084
Subitems | Name | Owner | Category | Status | Date | Item ID (auto generated)
| Jose Demasi - Marketing Department Manager |  | Marketing | Done |  | 9203558635
| Rodrigo Mena - Marketing & Creative Director |  | Marketing | Done |  | 9203563731
| David Marinelli - Marketing Specialist |  | Marketing | Done |  | 9341847944
| Erik Enson - General Manager |  | Office | Done |  | 9983796274
| Eve Sarfati - HR Manager |  | Office | Done |  | 9203546302
| Selena Gittner - Sales Executive Manager |  | Office | Done |  | 9203543963
| Chris Huerta - Sales Executive Manager |  | Office | Done |  | 9203548338
| Moshe Hai Zion - Lead Chimney Technician CSIA Certification: 12496 - X |  | Field | Done |  | 9983893213
| Menahem Maamari - Lead Chimney Technician CSIA 12399 - x |  | Field | Done |  | 9983891748
| Neorai Maamari - Lead Chimney Technician - CSIA 12487 - x |  | Field | Done |  | 9983893670
| Rotem Hadad - Lead Chimney Technician - CSIA 12491 - x |  | Field | Done |  | 9241310032
| Avihay Malka - Lead Chimney Technician CSIA Certification: 12496 - x |  | Field | Done |  | 9983893982
| Netanel Mulokandov - Lead Chimney Technician CSIA Certification: 12489 - x |  | Field | Done |  | 9983798621
| Tamir Alon - Lead Chimney Technician - 12397 - x |  | Field | Done |  | 9983894114
| Nahman Melci - Chimney Technician - CSIA 12389 - x |  | Field | Done |  | 9983892995
| Itzhak Swartz - Chimney Technician - CSIA 12398 - x |  | Field | Done |  | 9983893449
| Michael Thompson - Chimney Technician - CSIA 12392 x |  | Field | Done |  | 9983823341
| Ronald Rivera - Chimney Technician X |  | Field | Done |  | 9203915792
| Akiva Meltzer - Chimney Technician x |  | Field | Done |  | 9983893845
| Actors NJ - Bar will send |  | Working on it | Done |  | 9203607563
| Darren Couch - Apprentice Chimney Technician - CSIA 12390 x |  | Field | Done |  | 9983892369
| Pedro Saez - Masonery Specialist x |  | Field | Done |  | 9302534672
| Darwin Sanchez - Masonery Specialist x |  | Field | Done |  | 9983892581
| Emily Parker - Customer Experience Specialist |  | Office | Done |  | 9983378856
| Jessica Coleman - Customer Experience Specialist |  | Office | Done |  | 9983382606
| Hannah Brooks - Technician Supervisor |  | Office | Done |  | 9983384983
| Rachel Monroe - Technician Supervisor |  | Office | Done |  | 9983783889
| Ashley Plummer - Technician Supervisor |  | Office | Done |  | 9985253919
| Megan Sullivan - Customer Service Representative |  | Office | Done |  | 9983788322
| Lauren Mitchell - Customer Service Representative |  | Office | Done |  | 9983793969
| Samantha Hayes - Customer Service Representative |  | Office | Done |  | 9983794904
| Natalie Reed - Customer Service Representative |  | Office | Done |  | 9983797212
| Daniella Burnes - Customer Service Representative |  | Office | Done |  | 9985253029
| Santiago Lugo - Customer Service Representative |  | Office | Done |  | 9985251115
| Sara Persad - Customer Service Representative |  | Office | Done |  | 9985250486
A1 Chimney - New Subdomains |  | Jose Demasi | Done |  |  |  | 18226568771
Locations section |  | Jose Demasi | Done |  |  |  | 18226638987
New Website - Emergency Plumbing |  | Jose Demasi | Done |  |  |  | 10085155785
New Emails |  | Jose Demasi | Done | Critical ⚠️️ |  |  | 18381454879
Training Program |  | Jose Demasi | Done |  |  |  | 10073991217
Guidelines
Name | Subitems | Person | Status | Priority | Due Date | Date | Item ID (auto generated)
SEO Websites |  | Jose Demasi | Guidelines |  |  |  | 9250740903
Create Local SEO Pages |  | Jose Demasi | Guidelines |  |  |  | 9129505075
General Website Points |  | Jose Demasi | Guidelines |  |  |  | 9159428072
Company Files
Name | Subitems | Person | Status | Priority | Due Date | Date | Item ID (auto generated)
Daily Performance |  | Jose Demasi |  |  |  |  | 9204128246
Employment Agreement |  | Jose Demasi |  |  |  |  | 9138926852
Passwords |  | Jose Demasi |  |  |  |  | 9125792667

## jose demasi-updates
Jose Demasi | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
9125792667 | Passwords | Update |  | Bar Ohayon | 12/May/2025 01:57:28 PM | Gmail: Jose@a-1chimney.com Jose@Dea# Shutterstock: info@a-1chimney.com A1ShutterS123! Adobe: Jose@a-1chimney.com J@se@Dea#1 | 0 |  | 4112303589
9126417679 | US Garage Repair | Update |  | Bar Ohayon | 12/May/2025 10:14:33 AM | WP Login: https://www.usgaragerepair.net/wp-admin/ USGarage US47G@ra! | 0 |  | 4111215978
9126417679 | US Garage Repair | Update |  | Bar Ohayon | 15/May/2025 12:04:45 PM | Please add our license number to the website: License #HIC. 0701074 | 1 |  | 4123337770
9126417679 | US Garage Repair | Update |  | Jose Demasi | 19/May/2025 08:59:37 AM | Updated Both Websites, Waiting for Review ! | 0 |  | 4131094578
9126417679 | US Garage Repair | Update |  | Bar Ohayon | 20/May/2025 12:40:52 PM | Greater Connecticut.txt | 0 | 2152881768 | 4136303081
9129391380 | Air 75 | Update |  | Bar Ohayon | 12/May/2025 02:22:01 PM | Hi Jose, Please create a new website for this company. All the information needed were added to your shared folder. let me know if you need anything. Thank you. | 1 |  | 4112395484
9129391380 | Air 75 | Update |  | Bar Ohayon | 15/May/2025 12:02:37 PM | Please make the intro of the website more bright | 1 |  | 4123329463
9129391380 | Air 75 |  | Reply | Bar Ohayon | 15/May/2025 12:02:48 PM | This is little too dark | 1 |  | 4123330227 | 4123329463
9129391380 | Air 75 | Update |  | Jose Demasi | 19/May/2025 12:45:56 PM | Do we have a license number for this one ? | 0 |  | 4132215033
9129391380 | Air 75 | Update |  | Bar Ohayon | 20/May/2025 12:37:23 PM | License #TACLA84905E | 0 |  | 4136285231
9129391380 | Air 75 | Update |  | Bar Ohayon | 20/May/2025 12:40:27 PM | Greater DFW.txt | 0 | 2152880583 | 4136301413
9129391380 | Air 75 | Update |  | Bar Ohayon | 20/May/2025 12:51:31 PM | _yoast_wpseo_title | 0 |  | 4136343454
9129391380 | Air 75 | Update |  | Bar Ohayon | 20/May/2025 12:52:25 PM | function post_title_shortcode(){ return get_the_title(); } add_shortcode('post_title','post_title_shortcode'); | 0 |  | 4136346898
9138926852 | Employment Agreement | Update |  | Jose Demasi | 14/May/2025 12:57:46 PM | Sending the Signed and scanned Document as well as my Driver's License Scanned Doc: scan.pdf ID: | 0 | 2140668542,2140668543,2140670758 | 4119726709
9138926852 | Employment Agreement |  | Reply | Shoval Ohayon | 14/May/2025 01:26:58 PM | @Jose Demasi SSN is missing can you please send me here | 1 |  | 4119910705 | 4119726709
9138926852 | Employment Agreement |  | Reply | Shoval Ohayon | 14/May/2025 01:36:13 PM | @Jose Demasi great can you please also send me your email and phone number | 0 |  | 4119949271 | 4119726709
9138926852 | Employment Agreement |  | Reply | Jose Demasi | 14/May/2025 01:37:04 PM | Email: Joseluisdemasi94@gmail.com Phone: 305 724 2199 | 0 |  | 4119952136 | 4119726709
9138926852 | Employment Agreement | Update |  | Shoval Ohayon | 10/June/2025 11:51:13 AM |  | 0 | 2196130887 | 4193501265
9159428072 | General Website Points | Update |  | Bar Ohayon | 15/May/2025 11:29:36 AM | General Website Changes (Applicable to all Websites): 1. Business name must be separated with spaces "USGarageRepair" > "US Garage Repair" 2. Buttons needs to be not too big (padding: 50px ,15px) 3. Top button must be link to the company phone number 4. In our services section the aspect ratio of the images should be corrected and not cropped 5. Fix all links in the website to work and to have hover effect (in site settings) 6. All Images must be watermarked 7. Contact Us page must include a contact form 8. Blog page must include only the blog posts 9. Single post must include a custom sidebar 10. Services and Posts content must be more organized with Headlines, text, lists, etc... 11. All websites should include the local seo star rating at the footer. | 1 |  | 4123151727
9159428072 | General Website Points | Update |  | Bar Ohayon | 15/May/2025 12:00:13 PM | All new website must be stasrted at the Site Settings | 1 |  | 4123318635
9203528084 | A1 Chimney Employee Page | Update |  | Shoval Ohayon | 21/May/2025 01:26:38 PM | Contact Shoval before starting | 0 |  | 4140575273
9203671354 | Premier Garage Repair | Update |  | Bar Ohayon | 21/May/2025 01:26:57 PM | Please create new website for thew following company, All the information needed is in the shared folder. Let me know if you need anything. | 1 |  | 4140577177
9203671354 | Premier Garage Repair | Update |  | Shoval Ohayon | 27/May/2025 10:57:48 AM | Replace photo in maintenance service | 1 | 2165856819 | 4153586011
9204128246 | Daily Performance | Update |  | Jose Demasi | 21/May/2025 04:53:06 PM | Daily Performance 5/21/25 - Worked on the SEO for Us Garage and Air 75 as well as tweaked the mobile optimization for both of them - Created the Remaining 3 Blog Posts for US Garage and optimized them accordingly - Build the Single City Template for US Garage and made a few Tweaks to the Air75's counterpart. - Imported 172 Location List for US Garage and turned them into active pages. - Started initial work on the New "Premiere Garage Repair Website" | 0 |  | 4141410123
9204128246 | Daily Performance | Update |  | Jose Demasi | 22/May/2025 04:03:37 PM | Daily Performance 5/22/25 - Worked on the Design for the Premium Garage Repair Web - Designed the Watermark for the Services - Created main pages and initial SEO - Worked mainly on the Homepage layout - Video edition for Main Website - Started creating Service Pages and optimizing their SEO accordingly - Revisited Air 75 Website and redesigned the Local Areas page - Set up automatic excel sheets that help out with coding for future websites. | 0 |  | 4144877757
9204128246 | Daily Performance | Update |  | Jose Demasi | 23/May/2025 01:43:36 PM | Daily Performance 5/23/25 - Made 12 Service Pages and their worked on their SEO as well for Premiere Garage - Designed Featured Image for each of the Services. - Reworked Widget from Scratch in HTML to better fit the needs of the Website - Worked on Homepage Initial Layout - Initial View - Implemented Widgets - Contact Form - Services Layout - Started Blog Pages Articles and SEO - Designed Blog Pages Individual Images (12) | 0 |  | 4147616486
9204128246 | Daily Performance | Update |  | Jose Demasi | 26/May/2025 03:13:27 PM | Daily Performance 5/26/25 - Made 12 Blog Posts and Optimized their SEO - Set up Individual Images for Each - Finished Initial Home Layout - Started F.A.Q Page - Started About Us Page - Created Theme for Service and Blog Pages - Created Theme for Privacy Pages - Worked on Custom HTML for FAQ - Redesigned Character for usage in Website - Started Refining Main Pages SEO | 0 |  | 4151469410
9204128246 | Daily Performance | Update |  | Jose Demasi | 28/May/2025 09:05:37 AM | Daily Performance 5/27/25 - Reworked Main Pages - Prepared Excel for Local Areas Export - Imported 171 Connecticut Local Areas - Designed Service Areas Page - Worked on SEO Optimization - Photoshop Edition for New Images | 0 |  | 4156736921
9204128246 | Daily Performance | Update |  | Jose Demasi | 29/May/2025 09:57:54 AM | Daily Performance 5/28/25 - Made adjustments to the Premier Garage Repair Page - Optimized Text for SEO - Made Website Tablet - Mobile Friendly - Changed the Layout of all the Main Pages and Templates for a more simple scheme. - Started Working on Air 75 Car Wrap Design | 0 |  | 4160706709
9204128246 | Daily Performance | Update |  | Jose Demasi | 29/May/2025 04:24:52 PM | Daily Performance 5/29/25 - Revisited 3 Previous Websites to Fix Phone Call Functions. - Worked on Air 75 Car Wrap ReDesign - Made a few Revisions and fix on AIR75 Website. - Completed 5 Different Designs - Familiarized with A1Chimney Websites for Future Projects. | 0 |  | 4162463680
9204128246 | Daily Performance | Update |  | Jose Demasi | 03/June/2025 04:54:01 PM | Daily Performance 5/30/25 & 6/3/25 - Made 15 New Designs for Air 75 Air Wrap - Revised Websites for any Changes or Upgrades - Made Minor Fixes on Website - Focused on Final Air Wrap Design Layout | 0 |  | 4175884870
9204128246 | Daily Performance | Update |  | Jose Demasi | 04/June/2025 04:34:42 PM | Daily Performance 6/4/2025 - Worked on Final Air 75 Air Wrap Design - Checked current state of Speedy Garage Door Website - Updated Plugins - Menu and Coding Issues - Created Users / Menus / Deleted Themes - Started working on New Layout for the Homepage - Service Creation / SEO Optimization. - Created 10 Service Pages and Optimized them. - Designed Services Watermark | 0 |  | 4179575692
9204128246 | Daily Performance | Update |  | Jose Demasi | 05/June/2025 04:05:35 PM | Daily Performance 6/5/2025 - Finished Overall Layout of Main Website - Started Working on Sub Websites - Build Theme for Blog Posts - Created 8 Blog Pages and Optimized them SEO Wise - Created Watermark Featured Images for Blog Posts and Privacy Pages - Worked on About Us / Contact / Services Page. | 0 |  | 4183034746
9204128246 | Daily Performance | Update |  | Jose Demasi | 06/June/2025 01:30:05 PM | Daily Performance 6/6/2025 - Worked on Speedy Garage Door Websites - Finished Main Layout of all the Pages - Started Single Location Upload for Connecticut - Created 171 Pages - Designed Single Location Theme / Layout - Revised Previous Websites for a Google Maps error and fixed it accordingly - Optimized Website Layout - Downloaded Stock Footage and organized them into the appropriate folders for future use. | 0 |  | 4185813968
9204128246 | Daily Performance | Update |  | Jose Demasi | 09/June/2025 01:40:26 PM | Daily Performance 6/9/2025 - Worked on SEO Optimization for Garage Website - Implemented changes to Layout - Worked on Tablet and Mobile Design - Started research on Roofing Websites for Ideas. - Worked on Early Design idea for Future Roofing Website proyect. - Went through Stock Footage for future proyect. - Illustrator Designs - Change Website Introduction and replaced on entirety of site. - Worked on PopUps for current and previous websites. | 0 |  | 4189923674
9204128246 | Daily Performance | Update |  | Jose Demasi | 11/June/2025 09:10:11 AM | Daily Performance 6/10/2025 - Made adjustments on Website Layout - Downloaded Stock Footage for Future Projects as it it set to renew tomorrow. - Worked on Updating Previous US Garage Website for Improvement - Redesigned Homepage Layout for USGARAGE - Finished polishing details on Speedy Garage Repair Web - Finished Website - Started New Project and Logo Design | 0 |  | 4196670211
9204128246 | Daily Performance | Update |  | Jose Demasi | 12/June/2025 09:07:09 AM | Daily Performance 6/11/2025 - Started Initial Web Layout for TopUp Roofing - Created Initial Pages - Worked on Blog Posts and SEO ( 10 Blog Posts ) - Worked on Creating Services for Roofing Company - Spent Remaining Credits on Shutterstock since the credits were about to expire for monthly renewal - Stockpiled on Roofing / Garage Images. - Designed Logo for TopUp Roofing - Started Working on Initial Web Layout | 0 |  | 4200361699
9204128246 | Daily Performance | Update |  | Jose Demasi | 12/June/2025 04:22:58 PM | Daily Performance 6/12/2025 - Worked on Initial Web Layout of A1 Garage Door Repair - Created Initial Pages / Plugins / Settings - Created Articles for Services Pages - Created Articles for Blog Pages - SEO Optimization - Designed Watermarks for Both Websites. - Worked on Initial Homepage Layout | 0 |  | 4202245549
9204128246 | Daily Performance | Update |  | Jose Demasi | 16/June/2025 04:46:30 PM | Daily Performance 6/13/2025 - Worked on SEO Optimization for Both Current Websites and FInished the Creation of Articles and Service Page - Designed Overall Layout of TopUp Website and Secondary Pages - Started Initial Work on TopUp Layout Design | 0 |  | 4210986869
9204128246 | Daily Performance | Update |  | Jose Demasi | 16/June/2025 04:48:14 PM | Daily Performance 6/16/2025 - Worked on SEO Optimization for A1Garage Website and Polished Articles using new provided information. - Designed Homepage Layout - Revised TopUpGarage Website for Quick Fix - Designed Themes for A1 and Implemented - Designed Watermarks for A1 Service Images - Finished Initial Home Layout | 0 |  | 4210992469
9204128246 | Daily Performance | Update |  | Jose Demasi | 18/June/2025 04:19:13 PM | Daily Performance 6/17/2025 - Redesigned Homepage Layout - Redesigned Watermarks for Service and Blog Pages to fit the New Layout - Finished Homepage - Started work on Secondary Pages for A1 Garage Repair - Mobile Optimization | 0 |  | 4218731130
9204128246 | Daily Performance | Update |  | Jose Demasi | 18/June/2025 04:22:48 PM | Daily Performance 6/18/2025 - Watched Subdomain Training Video - Learned Process for Subdomain and Homepage Migration and created a Step by Step Guide for Future Reference - Revised Websites before Migration to fix Locations and Phone Contacts - Designed Single Location Page for A1 - Created 171 Locations for A1 Garage Website - Subdomain Creation and Migration of the 4 Garage Door Websites. ( Will need Feedback to make sure everything is correct ) | 0 |  | 4218741855
9204128246 | Daily Performance | Update |  | Jose Demasi | 19/June/2025 04:05:19 PM | Daily Performance 6/19/2025 - Finished Subdomain Migration for all the Garage Websites - Started making changes to Main / Subdomain for US Garage Repair to set them appart and redesigned the Service Area ( Main ) - Revised Phone / Locations and fixed broken links. - Revised Articles for the same previous changes - Repeat Process for Premier Garage Repair and Speedy Garage Door - Redesigned FAQ Pages for all Main Websites and added more CTA's - Seo Optimization. | 0 |  | 4221823177
9204128246 | Daily Performance | Update |  | Jose Demasi | 23/June/2025 04:35:34 PM | Daily Performance 6/20/2025 - Started Main / Subdomain changes to A1 Garage Door Repair and Optimized the Website Accordingly. - Modified Articles for Main Domain and changed Phone Numbers / Address - Finished Overall Changes - Worked on Service Areas Redesign for Main Domains to fit potential growth with State Based lists. - Worked on SEO Optimization for A1 Garage Website | 0 |  | 4229484212
9204128246 | Daily Performance | Update |  | Jose Demasi | 23/June/2025 04:35:39 PM | Daily Performance 6/23/2025 - Went through all the previous websites updating links and formatting for phone numbers / address / etc. for any required changes in the future so they can be modified with string changes. - Worked on Updating SEO to improve visibility. - Redesigned Hero Sections for Previous Websites as well as Subdomains. ( US Garage Repair - Air 75 ) - Improved articles and various texts from Premier Garage Repair Website and subdomain accordingly. - Changed Layout for Air75 Main Page and reorganized texts and images accordingly. - Worked on final Design for TopUp Roofing Watermarks for both Blog and Services - Created PopUps for all Sites / Subdomains | 0 |  | 4229484443
9204128246 | Daily Performance | Update |  | Jose Demasi | 25/June/2025 09:12:45 AM | Daily performance 6/24/2025 - Finished PopUps for Sites and Subdomains ( Need Review for Approval ) - Went through Shutterstock to build up stock on Services Images / Customers and resized them accordingly for future usage on websites. - Updated SEO for all Websites to improve visibility - Went through Main and Subdomain for comparisons and finished - Made Design Change on AIR 75 Web - Build up Stock Library | 0 |  | 4235378276
9204128246 | Daily Performance | Update |  | Jose Demasi | 26/June/2025 09:08:46 AM | Daily performance 6/25/2025 - Changed Shutterstock Contract to Unlimited Plan for 16$ per Month against the $169 per month Image only Plan that was in place, spent the remaining credits for building up a stock library for future usage. - Started working on Image Alteration for Main domain contact images for the phone number / address replacements - Reworked all Watermarked Images for Speedy Garage Repair / US Garage Repair - Went through the new Video Library to search for High Quality Replacements for the current videos in each website's homepage and sub pages. - Updated Initial Website to better fit standards and created new Blog Articles on Domain and Subdomain accordingly - Premiere Video Edition and Rendering for Website Introductory Videos. - Worked on simple motion effects for the websites to change the static overall look. | 0 |  | 4241031889
9204128246 | Daily Performance | Update |  | Jose Demasi | 26/June/2025 04:21:25 PM | Daily performance 6/26/2025 - Continued improvement on website motion. - Read Articles on how to Improve SEO from Yoast - Revisited US Garage Door and made several updates, created new articles and updated existing ones to better improve SEO. - Designed new Watermarks for Main / Subdomain Articles, and replaced previous ones. - Repeated Update Process on Websites Overall - Worked on design ideas for Chimney Website. - Solved some minor HTTPS Conflicts. | 0 |  | 4248536380
9204128246 | Daily Performance | Update |  | Jose Demasi | 30/June/2025 04:44:22 PM | Daily performance 6/27/2025 - Video Edition for A1 Chimney Website using New HD Video Footage - Started working on possible layout for A1 Chimney Website on a Hidden Subdomain for Testing purposes. - Watermark Design - Final Revisions on Previous Websites and Polishing - Seo Optimization - Completed Creation of Test Subdomain to work on A1 Chimney Website. | 0 |  | 4278901754
9204128246 | Daily Performance | Update |  | Jose Demasi | 30/June/2025 04:44:25 PM | Daily Performance 6/30/2025 - Started Working on A1Chimney Website - Revised existing website to nail down all features and services provided for design plannification. - Designed Homepage Initial Layout - Created Mockup Articles and Services for Starting Purposes - SEO Optimization - Changed Header in US Garage Repair to Include new Address. - Video Edition for Hero Initial Video. - Creation of Secondary Pages / Mockups | 0 |  | 4278902024
9204128246 | Daily Performance | Update |  | Jose Demasi | 01/July/2025 04:52:25 PM | Daily Performance 7/01/2025 - Continued work on Initial Layout for A1Chimney Homepage - Worked on Image Edition for Employee Page - Video Edition for CTA - Made changes to US Garage Repair - Created Initial Pages - Created additional Blog Posts + SEO Optimization - Build up Location List for Future Usage on different States - Completed Initial Homepage Layout See at: test.a-1garagedoorrepair.com - Tablet / Mobile Responsiveness - Worked on ES Language Availability - Polished Homepage | 0 |  | 4283333710
9204128246 | Daily Performance | Update |  | Jose Demasi | 02/July/2025 04:12:32 PM | Daily Performance 7/02/2025 - Minor Adjustments to Homepage - Designed and created TopUp Roofing Watermarks for Services and Blog Posts - Final Revision on TopUp Roofing Website - Will need Phone number when possible to update it on the whole site as well as any extra information. - Continued work on A1 - Designed Watermark prototype to fit new layout - Worked on layout for About / Contact / Service / ETC pages - Worked on Blog Articles and Services pages - Video Edition for subpages - Started planification for New Crestline Website - Crestline Watermark Design - Finished Core pages for A1 | 0 |  | 4287093751
9204128246 | Daily Performance | Update |  | Jose Demasi | 09/July/2025 09:06:24 AM | Daily Performance 7/07/2025 - Fixed Mobile Issues on Speedy Garage / US Garage Websites - Check on other Websites to find any other remaining Issues through Mobile / Tablet responsive layouts and fixed them accordingly. - Started Development of Crestline Website - Set up Initial Wordpress configuration and went over different possible designs | 0 |  | 4303406282
9204128246 | Daily Performance | Update |  | Jose Demasi | 09/July/2025 09:06:26 AM | Daily Performance 07/08/2025 - Created Subdomains for A1Chimney for Indiana and Virginia as well as Location Pages for Both of them - Checked for any Errors and fixed them accordingly - Continued work on Crestline Website - Finished overall Homepage Layout - Worked on Page Content | 0 |  | 4303406359
9204128246 | Daily Performance | Update |  | Jose Demasi | 09/July/2025 04:41:48 PM | Daily Performance 07/09/2025 - Worked on Crestline Website - Video Edition for Crestline Header - Set up the Main Service Articles as well as sub services - SEO Optimization - Fixed Issues on Premier Garage and A1 Garage Websites - Created the Service Articles for Crestline's Main and Sub Services and worked on their SEO Optimization - Watermark Design - Worked on Mobile optimization for Crestline and previous websites as well as optimization of existing formats. | 0 |  | 4305093040
9244919012 | TopUp Roofing Website | Update |  | Shoval Ohayon | 04/June/2025 01:42:05 PM | There is no license for roofing in Texas. No address it’s a mobile service only serves the few metroplex in texas | 1 |  | 4178889218
9244919012 | TopUp Roofing Website |  | Reply | Jose Demasi | 04/June/2025 01:43:53 PM | Got it, i'll remember that, I meant for Speedy Garage Door Repair, the other website ! | 0 |  | 4178902671 | 4178889218
9244919012 | TopUp Roofing Website |  | Reply | Shoval Ohayon | 04/June/2025 01:50:30 PM | @Jose Demasi Speedy Garage Doors LLC. HIC. 0701042 100 Pearl Street #1458, Hartford, Connecticut 06103 | 1 |  | 4178927769 | 4178889218
9244919012 | TopUp Roofing Website | Update |  | Bar Ohayon | 10/June/2025 02:19:23 PM | Please start with creating a Logo | 0 |  | 4194176694
9244919012 | TopUp Roofing Website | Update |  | Jose Demasi | 10/June/2025 03:32:14 PM | TopUp Roofing is in Texas ? | 0 |  | 4194595569
9244919012 | TopUp Roofing Website | Update |  | Jose Demasi | 20/June/2025 12:38:32 PM | Need Phone Number for TopUp whenever possible ! | 0 |  | 4223971335
9249455605 | Air 75 Car Wrap Design | Update |  | Shoval Ohayon | 28/May/2025 11:34:38 AM | “Cruising to Comfort with Air 75” #TACLA84905E (469) 343-0107 air75hvac.com | 0 | 2168693610 | 4157420413
9249455605 | Air 75 Car Wrap Design |  | Reply | Jose Demasi | 29/May/2025 09:57:37 AM | Initial DesignAir 75 Wrap.aiAir 75 Wrap.svgAir 75 Wrap.pdf | 0 | 2171150691,2171150696,2171150704,2171153315 | 4160703265 | 4157420413
9249455605 | Air 75 Car Wrap Design |  | Reply | Jose Demasi | 29/May/2025 01:01:17 PM | Design 2 Design 2.pdf | 0 | 2171727895,2171728445 | 4161533709 | 4157420413
9249455605 | Air 75 Car Wrap Design |  | Reply | Jose Demasi | 29/May/2025 02:01:57 PM | Design 3 | 0 | 2171889809 | 4161785866 | 4157420413
9249455605 | Air 75 Car Wrap Design |  | Reply | Shoval Ohayon | 30/May/2025 02:20:48 PM | Thanks Jose I got this I will review and get back to you on Tuesday! Enjoy the weekend! | 1 |  | 4165453646 | 4157420413
9249455605 | Air 75 Car Wrap Design | Update |  | Jose Demasi | 30/May/2025 11:28:48 AM | New Design Idea - WIP | 0 | 2174253837 | 4164611990
9249455605 | Air 75 Car Wrap Design | Update |  | Jose Demasi | 30/May/2025 11:56:05 AM | Alternative Design | 0 | 2174273228 | 4164706123
9249455605 | Air 75 Car Wrap Design | Update |  | Jose Demasi | 30/May/2025 12:17:49 PM | Third Alternative Design | 0 | 2174388450 | 4164794606
9249455605 | Air 75 Car Wrap Design | Update |  | Jose Demasi | 30/May/2025 12:32:19 PM |  | 0 | 2174436199 | 4164872235
9249455605 | Air 75 Car Wrap Design | Update |  | Jose Demasi | 30/May/2025 01:12:39 PM |  | 0 | 2174546731 | 4165078956
9249455605 | Air 75 Car Wrap Design | Update |  | Jose Demasi | 30/May/2025 01:53:49 PM |  | 0 | 2174653710 | 4165272272
9249455605 | Air 75 Car Wrap Design | Update |  | Jose Demasi | 30/May/2025 02:33:21 PM | You too have a great weekend ! | 0 |  | 4165499766
9249455605 | Air 75 Car Wrap Design | Update |  | Jose Demasi | 03/June/2025 11:25:13 AM | New Design Idea | 0 | 2181693757 | 4174401622
9249455605 | Air 75 Car Wrap Design | Update |  | Jose Demasi | 03/June/2025 11:59:24 AM | Alternative | 0 | 2181804993 | 4174590186
9249455605 | Air 75 Car Wrap Design | Update |  | Jose Demasi | 03/June/2025 01:43:16 PM |  | 0 | 2182129667 | 4175077039
9302883853 | Speedy Garage Door Repair | Update |  | Jose Demasi | 09/June/2025 01:37:04 PM | Whenever possible you can already review the website for overall progress ! | 0 |  | 4189912051
9345240830 | A1 Garage Door Repair | Update |  | Bar Ohayon | 10/June/2025 02:33:48 PM | Hi please create a new website for this company let me know if you need anything | 1 |  | 4194244216
9389861407 | Add address to garage door websites | Update |  | Shoval Ohayon | 16/June/2025 09:11:15 PM | Ask bar for addresses | 0 |  | 4211487767
9389861407 | Add address to garage door websites | Update |  | Bar Ohayon | 17/June/2025 03:46:10 PM | Please Update the following numbers for the main garage doors websites: Premier Garage Doors - (888) 734-0444 Speedy Garage Doors - (888) 714-8777 US Garage Doors - (888) 734-4555 | 0 |  | 4214568696
9389861407 | Add address to garage door websites |  | Reply | Jose Demasi | 18/June/2025 12:07:55 PM | Any updates to the A1-Garage Repair Phone and Address or are those okay. Right now i have (475) 212-4747 | 0 |  | 4217640039 | 4214568696
9389861407 | Add address to garage door websites | Update |  | Bar Ohayon | 17/June/2025 03:48:08 PM | Please Update the following addresses in the subdomains: Premier Garage Doors - 1000 Lafayette Blvd #1108, Bridgeport, CT 06604 Speedy Garage Doors - 100 Pearl St #1458, Hartford, CT 06103 US Garage Doors - 157 Church St #1928, New Haven, CT 06510 | 0 |  | 4214578319
9485128621 | Change header for us garage door | Update |  | Chaim Perez | 30/June/2025 02:05:21 PM | Please put the address of the business on all pages of the web 157 Church St #1928, New Haven, CT 06510 | 1 |  | 4278253377
9485128621 | Change header for us garage door |  | Reply | Jose Demasi | 30/June/2025 02:06:43 PM | On Both Main and Subdomain ? | 0 |  | 4278261208 | 4278253377
9485128621 | Change header for us garage door |  | Reply | Chaim Perez | 30/June/2025 03:42:41 PM | Yes | 1 |  | 4278678619 | 4278253377
9495288839 | Hours of operation | Update |  | Chaim Perez | 01/July/2025 12:53:29 PM | The hours Sunday - Thursday 24H Friday 12: 00 AM - 4:30pm Saturday 9:00pm - 12:00 am @Jose Demasi | 0 |  | 4282284980
9495288839 | Hours of operation |  | Reply | Chaim Perez | 01/July/2025 12:54:02 PM | i need it ASAP please let me know when done | 1 |  | 4282292577 | 4282284980
9495288839 | Hours of operation |  | Reply | Jose Demasi | 01/July/2025 12:57:24 PM | On it | 1 |  | 4282337133 | 4282284980
9495288839 | Hours of operation |  | Reply | Jose Demasi | 01/July/2025 01:05:09 PM | @Chaim Perez Done | 0 |  | 4282396946 | 4282284980
9495288839 | Hours of operation |  | Reply | Chaim Perez | 01/July/2025 01:16:16 PM | Thank you 🙏 | 1 |  | 4282444755 | 4282284980
9501038842 | CrestLine Home Website | Update |  | Shoval Ohayon | 02/July/2025 02:04:27 AM |  | 1 | 2264020151 | 4284208038
9501038842 | CrestLine Home Website |  | Reply | Jose Demasi | 02/July/2025 09:10:06 AM | Got it, do you have the details for the company and the wordpress login ? | 0 |  | 4285229440 | 4284208038
9501038842 | CrestLine Home Website |  | Reply | Shoval Ohayon | 02/July/2025 09:39:02 AM | @Jose Demasi yes once you finish the first website and about to start with that update Bar and he’ll send the information | 1 |  | 4285359602 | 4284208038
9501038842 | CrestLine Home Website | Update |  | Bar Ohayon | 03/July/2025 03:53:30 PM | Hi Jose the information for thius website was uploaded to the shared folder. Let me know if you need any more information. Thank you. | 1 |  | 4290647458
9518086816 | TopUp Roofing - Phone Number | Update |  | Bar Ohayon | 03/July/2025 03:51:40 PM | (888) 727-0730 | 1 |  | 4290640662
9518112414 | A1 Chimney - Indiana | Update |  | Bar Ohayon | 03/July/2025 03:57:27 PM | Hi Jose, Please create a new subdomain and duplicate the website to this area: IN (Indiana) (888) 538-4457 Here is the cities list: Beverly Shores Cedar Lake Chesterton Crown Point Dyer East Chicago Gary Griffith Hammond Highland Hobart Lake Station Leroy Lowell Merrillville Munster Portage Saint John Schererville Valparaiso Wheeler Whiting | 1 |  | 4290661026
9518112414 | A1 Chimney - Indiana | Update |  | Bar Ohayon | 03/July/2025 04:02:19 PM | I've already created the subdomain in the siteground just do all the rest | 1 |  | 4290679377
9524231798 | Need to fix it asap | Update |  | Bar Ohayon | 04/July/2025 06:18:55 PM | Fix the shape at the bottom to see the phone number and change the “all done right the first time”. | 0 | 2270197882 | 4293205148
9524231798 | Need to fix it asap | Update |  | Bar Ohayon | 04/July/2025 06:19:23 PM | As well as here the first headline is too big and the phone number is overflowing. | 0 | 2270199469 | 4293205375
9541810369 | A1 Chimney - Maryland | Update |  | Bar Ohayon | 08/July/2025 10:07:18 AM | Hi Jose, Please create a new subdomain and duplicate the website to this area: MD (Maryland) (888) 711-7966 Under this subdomain we will have 2 batches of areas so make sure to have 2 areas under the "Our Locations" page. Here are the cities: Greater Baltimore.txt Greater Rockville.txt Thnak you. | 1 | 2274819070,2274819072 | 4299860739
9541814792 | A1 Chimney - Virginia | Update |  | Bar Ohayon | 08/July/2025 10:08:48 AM | Hi Jose, Please create a new subdomain and duplicate the website to this area: VA (Virginia) (888) 651-9466 Here are the cities list for the website: Greater Alexandria.txt Thank you. | 1 | 2274829219 | 4299867841
9564455411 | Duplicate A1 Garage Door Website | Update |  | Bar Ohayon | 10/July/2025 03:13:44 PM | Hi Jose, Please duplicate this website and create a subdomain for this area: GA (Atlanta) (470) 668-5030 Greater Atlanta.txt | 1 | 2281119208 | 4308304854
9581883400 | A1 Roofing Website - Texas | Update |  | Shoval Ohayon | 14/July/2025 09:33:21 AM | Check with Shoval once you’re on it | 0 |  | 4314799403
9592456572 | A1 Garage Doors - Changes | Update |  | Bar Ohayon | 15/July/2025 10:09:43 AM | Hi Jose, Please change the phone number on the main website for A1 Garage Doors to this one: (888) 798-0444 Thank you. | 1 |  | 4319049283
9592456572 | A1 Garage Doors - Changes | Update |  | Shoval Ohayon | 15/July/2025 04:34:53 PM | 303 Perimeter Center North #322, Atlanta, Georgia 30346 | 0 |  | 4320724033
9596667235 | Plugins Update | Update |  | Bar Ohayon | 15/July/2025 04:03:59 PM | I have Update you plugins folder with the updated versions for the Yoast Pro and the Elementor Pro. Please update those plugins by removing them from the websites and reinstall them. Please do it to the following websites: Premier Garage Door Repair A1 Garage Doors Thank you. | 1 |  | 4320597091
9596667235 | Plugins Update | Update |  | Bar Ohayon | 15/July/2025 04:04:47 PM | Please Disable all the plugins auto-update for all websites | 1 |  | 4320601647
9614490749 | Create Address Pages | Update |  | Bar Ohayon | 17/July/2025 01:44:32 PM | Our Locations: Locations.xlsx Example: https://www.soslocksmith-tx.com/2302b-myrtle-springs-ave-dallas-tx-75220/ | 0 | 2295126770 | 4327404403
9614490749 | Create Address Pages |  | Reply | Jose Demasi | 22/July/2025 10:17:41 AM | There's no Phone information on the Address 13477 Prospect Rd # 204, Strongsville, OH 44149 https://www.google.com/maps/place/A1+Chimney/@41.3161564,-81.8596915,17z/data=!3m2!4b1!5s0x8830eaa8fa94607d:0x4513c2100527a473!4m6!3m5!1s0x8830eb554b18f9f9:0xbb235d5492c74abb!8m2!3d41.3161564!4d-81.8571166!16s%2Fg%2F11wfhtbmk1?entry=ttu&g_ep=EgoyMDI1MDYwOS4xIKXMDSoASAFQAw%3D%3D | 0 |  | 4337717502 | 4327404403
9614490749 | Create Address Pages |  | Reply | Jose Demasi | 22/July/2025 11:44:29 AM | Missing Number as well from 3939 US-80 Suite 102, Mesquite, TX 75150 https://www.google.com/maps/place/A1+Chimney/@32.7952588,-96.6611668,17z/data=!3m2!4b1!5s0x864ea40960e92251:0xa3235cb6aa13e41e!4m6!3m5!1s0x864ea51a04d652ad:0xc4a739274f17554!8m2!3d32.7952588!4d-96.6585919!16s%2Fg%2F11x00rl9vl?entry=ttu&g_ep=EgoyMDI1MDYwOS4xIKXMDSoASAFQAw%3D%3D | 0 |  | 4338242088 | 4327404403
9614490749 | Create Address Pages |  | Reply | Bar Ohayon | 22/July/2025 11:46:58 AM | @Jose Demasi (440) 658-4555 | 1 |  | 4338253439 | 4327404403
9614490749 | Create Address Pages |  | Reply | Bar Ohayon | 22/July/2025 11:47:36 AM | @Jose Demasi (469) 949-7009 | 1 |  | 4338256606 | 4327404403
9614490749 | Create Address Pages | Update |  | Bar Ohayon | 29/July/2025 01:54:25 PM | A1 Chimney - Locations.xlsx | 1 |  | 4358317364
9614490749 | Create Address Pages |  | Reply | Jose Demasi | 26/August/2025 10:09:07 AM | Any Update on the Missing Locations ? | 0 |  | 4432936995 | 4358317364
9643167365 | Fix issue ASAP | Update |  | Bar Ohayon | 22/July/2025 09:10:20 AM | Hi Jose, There is an issue with the emails we are receiving from the contact forms of one of those websites US Garage Doors or Air 75, please check what is going on over there, it went to the US garage doors email but the page url in the email is air75havc.com/contact-us. So the problem is may be in this page. Thank you. | 1 | 2302721680 | 4337369571
9643167365 | Fix issue ASAP |  | Reply | Jose Demasi | 22/July/2025 09:10:51 AM | On it | 0 |  | 4337371368 | 4337369571
9643167365 | Fix issue ASAP |  | Reply | Jose Demasi | 22/July/2025 09:13:24 AM | Fixed 👍, I'll check all the contact forms just to be sure there aren't any more issues like that. | 0 |  | 4337379423 | 4337369571
9643167365 | Fix issue ASAP | Update |  | Bar Ohayon | 22/July/2025 10:03:51 AM | Thank you Jose, what was the issue over there? | 1 |  | 4337603908
9643167365 | Fix issue ASAP |  | Reply | Jose Demasi | 22/July/2025 10:06:08 AM | The Form in AIR75 had the contact details for US Garage, It probably happened because i copied the form between the websites, won't happen again, i already went through the other contact forms and apparently the issue was only there. | 0 |  | 4337615470 | 4337603908
9643167365 | Fix issue ASAP |  | Reply | Bar Ohayon | 22/July/2025 10:06:50 AM | @Jose Demasi ok not a problem Jose. Thank you. | 1 |  | 4337618438 | 4337603908
9654590386 | Speedy Chimney Sweep Logo | Update |  | Shoval Ohayon | 23/July/2025 11:15:16 AM | Tell Shoval before doing | 1 |  | 4342088930
9654590386 | Speedy Chimney Sweep Logo | Update |  | Jose Demasi | 04/August/2025 09:57:13 AM |  | 0 | 2330111866 | 4372714369
9655320459 | US Garage Repair - Boston | Update |  | Bar Ohayon | 23/July/2025 12:14:57 PM | This is the cities list for all the websitesGreater Boston.txt | 1 | 2306476457 | 4342434423
9655320459 | US Garage Repair - Boston |  | Reply | Bar Ohayon | 23/July/2025 12:19:40 PM | Create Subdomain: ma (For all websites) | 1 |  | 4342450828 | 4342434423
9655320459 | US Garage Repair - Boston | Update |  | Bar Ohayon | 23/July/2025 12:19:45 PM | Phone Number: (781) 385-5201 Address: 186 Lincoln St #106, Boston, MA 02110 | 0 |  | 4342451033
9655322381 | Speedy Garage Doors - Boston | Update |  | Bar Ohayon | 23/July/2025 12:21:09 PM | Phone Number: (781) 202-5032 Address: 99 Derby St #260, Hingham, MA 02043 | 0 |  | 4342455796
9655323917 | Premier Garage Door Repair - Boston | Update |  | Bar Ohayon | 23/July/2025 12:21:56 PM | Phone Number: (781) 222-0516 Address: 1500 District Ave #2052, Burlington, MA 01803 | 0 |  | 4342458410
9655324872 | A1 Garage Doors - UPDATE | Update |  | Bar Ohayon | 23/July/2025 12:37:44 PM | Please change the hours in the webiste to: Sunday-Thursday: 08:00 AM - 08:00 PM Friday: 08:00 AM - 05:00 PM | 0 |  | 4342515933
9655457790 | Watermarking | Update |  | Bar Ohayon | 23/July/2025 12:25:52 PM | Hi Jose, I created a new folder for you in the shared folder, I need you to watermark all the images in each folder (If Applicable). Thank you. | 0 |  | 4342473132
9655457790 | Watermarking |  | Reply | Jose Demasi | 24/July/2025 01:59:36 PM | Options | 0 | 2309483324,2309483349,2309483368,2309490066 | 4346364884 | 4342473132
9655457790 | Watermarking |  | Reply | Jose Demasi | 24/July/2025 02:00:06 PM |  | 0 | 2309491454 | 4346370789 | 4342473132
9657046470 | Sign | Update |  | Bar Ohayon | 23/July/2025 02:51:54 PM | Please make something like this as fast as you can for those locations: | 0 | 2306978626 | 4343066437
9657046470 | Sign | Update |  | Bar Ohayon | 23/July/2025 02:54:08 PM | AngiSweep: https://www.angisweep.com/virginia/alexandria-va/ https://www.angisweep.com/maryland/bethesda-md/ https://www.angisweep.com/district-of-columbia/washington-dc/ | 0 |  | 4343074142
9657046470 | Sign |  | Reply | Jose Demasi | 23/July/2025 03:19:56 PM |  | 0 | 2307059858,2307059861,2307059863 | 4343169178 | 4343074142
9657046470 | Sign | Update |  | Bar Ohayon | 23/July/2025 02:55:22 PM | A1 Chimney: https://md.a-1chimney.com/our-locations/baltimore-md/ https://va.a-1chimney.com/our-locations/alexandria-va/ https://dc.a-1chimney.com/our-locations/washington-dc/ | 0 |  | 4343078626
9657046470 | Sign |  | Reply | Jose Demasi | 23/July/2025 03:08:09 PM |  | 0 | 2307027119,2307027121,2307027122 | 4343127500 | 4343078626
9657046470 | Sign |  | Reply | Bar Ohayon | 23/July/2025 03:09:34 PM | @Jose Demasi Can you do it with the original logo? | 1 |  | 4343132177 | 4343078626
9657046470 | Sign |  | Reply | Jose Demasi | 23/July/2025 03:28:27 PM | @Bar Ohayon | 0 | 2307087676,2307087684,2307087711 | 4343211715 | 4343078626
9657046470 | Sign |  | Reply | Bar Ohayon | 23/July/2025 03:30:04 PM | And with the local number | 0 |  | 4343217620 | 4343078626
9657046470 | Sign |  | Reply | Bar Ohayon | 23/July/2025 03:30:33 PM | @Bar Ohayon let me send it to you | 1 |  | 4343219294 | 4343078626
9657046470 | Sign |  | Reply | Bar Ohayon | 23/July/2025 03:33:10 PM | Baltimore - (410) 699-9993 Washington - (202) 991-1557 Alexandria - (571) 540-9569 | 0 |  | 4343227908 | 4343078626
9657046470 | Sign | Update |  | Bar Ohayon | 23/July/2025 03:29:13 PM | Need it to be white background | 1 |  | 4343214893
9657046470 | Sign |  | Reply | Jose Demasi | 23/July/2025 03:35:30 PM |  | 0 | 2307109653,2307109655,2307109661 | 4343235440 | 4343214893
9698913437 | Duplicate Cresline Home | Update |  | Bar Ohayon | 29/July/2025 03:28:56 PM | Please duplicate the website to the following subdomains: Create "Our Locations" page and "Address Pages" for the following addresses: Maryland: md.crestln.com 4701 Sangamore Rd, 1st floor #152, Bethesda, MD 20816 (227) 248-9190 office@md.crestln.com Virginia: va.crestln.com 5904 Richmond Hwy, 5th Floor #525, Alexandria, Virginia (703) 721-7800 office@va.crestln.com DC: dc.crestln.com 1050 Connecticut Ave NW #5140, Washington, District of Columbia 20036 (771) 210-2225 office@dc.crestln.com Create "Service Areas" page with those cities: Greater Washington DC.txt | 0 | 2318907076 | 4358678319
9771016945 | Summaries points of ''how to sell video'' | Update |  | Chaim Perez | 07/August/2025 03:59:10 PM | lace Crack Repair – Quick Sales Points Show cracks and take photos. Explain heat and smoke escape risks. Warn about dangers — cracks weaken structure and can leak harmful gases like carbon monoxide. Explain repair — clean cracks and seal with heat-resistant mortar to restore safety. Highlight benefits — safer, more efficient, and better-looking fireplace. Handle objections — cracks get worse and are a safety risk, not just cosmetic. Close confidently — recommend fixing soon and ask when to schedule. Remember: You’re protecting homes — small cracks lead to big problems. Keep it simple and clear. Chimney Crown Repair – Quick Sales Summary Identify & show cracks on the crown; take photos. Explain risk: water penetration causes brick damage, rust, leaks inside home. Present solution: clean crown, remove loose material, apply waterproof, flexible repair product. Highlight benefits: prevents costly future repairs, protects chimney and home. Handle objections: water damage worsens over time; fixing now saves money later. Close confidently: recommend repair now and ask to schedule. Tech tip: Educate don’t sell. Keep it simple, visual, honest, and focused on protecting the home. Chimney Crown Replacement – Quick Sales Summary Show the problem: Point out major damage—wide cracks, missing pieces, crumbling. Take photos. Explain the risk: Patching won’t stop water intrusion; it just delays bigger damage and leaks inside the home. Present the solution: Remove old crown and build a new, custom, high-strength, waterproof crown. Highlight benefits: Long-term protection that prevents costly repairs and keeps chimney and home safe. Handle objections: “Just patch it?” — Patch won’t last; replacement offers peace of mind. “Expensive?” — Prevents much costlier damage later. Close confidently: Recommend replacement now and ask to schedule. Tech reminder: Focus on protecting the whole chimney and home. Be clear, visual, confident, and lead with value. Tuckpointing – Quick Sales Summary Show the problem: Point out cracked, missing, or crumbling mortar; take photos. Explain the risk: Broken mortar lets water in, causing bricks to loosen, leaks, and structural damage. Present the solution: Remove damaged mortar and replace with fresh, durable mortar matched to the chimney. Highlight benefits: Stops moisture, prevents costly repairs, and improves appearance. Handle objections: “Not that bad?” — Prevents expensive brick replacements or rebuilds later. “Can wait?” — Waiting leads to more damage and higher repair costs. Close confidently: Recommend scheduling soon to protect chimney; ask when to start. Tech tip: Emphasize prevention, long-term protection, and keeping the chimney strong and looking good. Custom Chimney Cap Installation – Quick Sales Summary Show the problem: No cap, damaged, or ill-fitting cap; take photos and explain vulnerability. Explain the risk: Water damage, pest intrusion, fire hazard from sparks, and crown exposure causing costly repairs. Present the solution: Custom-fabricated cap that fits perfectly, protects against weather, animals, debris, sparks, and UV damage. Highlight benefits: Long-term chimney protection, fire safety, pest prevention, durability, and aesthetic fit. Pricing & timeline: $1,800–$3,500 depending on size; about 10 business days fabrication before installation. Close confidently: Recommend ordering now to protect and beautify the chimney; ask to place the order. Tech tip: Emphasize this as a smart investment in home protection and appearance, not just an upgrade. Damper Cap Installation – Quick Sales Summary Show the problem: Broken, missing, rusted, or stuck damper; explain nothing seals the flue. Explain the risk: Cold drafts, heat loss, fire hazard from sparks/ashes, rain and animals entering chimney, unsafe fireplace use. Present the solution: Install a high-quality damper cap that seals the flue from the top, preventing water, pests, drafts. Highlight benefits: Improves safety, energy efficiency, pest prevention, and is affordable compared to internal damper repair/replacement. Close confidently: Recommend installation now to protect home and restore fireplace safety; ask to schedule. Tech tip: This is a simple, valuable upgrade that solves major problems safely and cost-effectively. Gas Log Installation – Quick Sales Summary Show benefits: Instant heat, easy use, no wood mess, cleaner burning, low maintenance, remote control, realistic flame. Identify customer needs: Convenience, better aesthetics, efficient heating, cost savings vs. wood. Present solution: Safe, code-compliant installation with proper gas line and ventilation. Highlight benefits: Beautiful flames, no cleanup, safer than wood, energy-efficient, adds home value. Address concerns: Quick, safe installation; less chimney sweeping; no soot or ash. Close confidently: Ask if they want to upgrade now for clean, efficient heat. Tech tip: Emphasize comfort, safety, and ease of use as a smart, low-maintenance upgrade. Brick Waterproofing – Quick Sales Summary Show the problem: Point out water damage signs—white stains, crumbling bricks, cracks; take photos. Explain the risk: Water breaks down bricks and mortar, causes mold, leads to costly repairs. Present the solution: Apply water-repellent sealant that blocks moisture but lets walls breathe. Highlight benefits: Prevents damage, mold, efflorescence; protects structure; reduces future repairs; preserves home value. Pricing: $600–$1,200 depending on area and condition; one-time, long-lasting treatment. Close confidently: Recommend scheduling now to stop damage and protect investment; ask when to start. Tech tip: Position waterproofing as a smart, preventative investment in home protection and appearance. Flashing Repair – Quick Sales Summary Show the problem: Point out rusted, separated, or damaged flashing; take photos and explain water leakage risk. Explain the risk: Water leaks cause wood rot, mold, insulation damage, and expensive repairs. Present the solution: Remove damaged flashing and install new sealed metal flashing to stop leaks fast and affordably. Highlight benefits: Prevent major damage, protect roof and structure, avoid costly repairs, gain peace of mind. Pricing: Typically $800–$1,800 depending on damage and materials; much cheaper than major repairs. Close confidently: Recommend scheduling repair soon to protect home before next storm; ask when to start. Tech tip: Emphasize flashing repair as a smart, urgent fix to stop leaks early and save money. Chimney Liner Installation – Quick Sales Summary Show the problem: Cracked, damaged, missing, or outdated liner; explain it’s a serious safety and code issue. Explain risks & codes: NFPA & IRC require liners to contain heat, smoke, gases; prevents fires, carbon monoxide leaks, and damage. Present solution: Install properly sized, stainless steel liner that resists heat and corrosion, ensuring code compliance. Highlight benefits: Improves safety, efficiency, prevents damage, and ensures legal compliance. Pricing (optional): $2,000–$5,000 depending on chimney size and liner type; one-time protective upgrade. Close confidently: Recommend scheduling soon to protect home and meet code; ask when to start. Tech tip: Focus on educating customers about safety and code compliance; explain why this upgrade is essential. Heat Shield Installation – Quick Sales Summary When needed: For chimneys with narrow or cracked liners where full liner replacement isn’t possible or practical. Present solution: Apply two coats of heat shield coating to create a thermal barrier protecting wood and structure. Benefits: Reduces fire risk, preserves home structure, code-compliant, fast and cost-effective alternative to liner replacement, extends chimney life. Risks if ignored: Heat can ignite wood framing; smoke and carbon monoxide leaks; costly damage and safety hazards. Close confidently: Recommend installation now to protect home, meet code, and avoid major repairs; ask when to schedule. Tech tip: Emphasize heat shield as a critical safety upgrade, not just a fallback, and focus on family safety and code compliance. Chase Cover Installation – Quick Sales Summary Explain what it is: Metal/aluminum cover sealing the top of chimney chase on prefab fireplaces to keep water out. Show the problem: Rusted, sagging, or missing covers let water in, causing wood rot, mold, and structural damage. Present the solution: Install durable, rust-resistant chase cover (stainless steel or powder-coated) that fully seals and protects. Highlight benefits: Prevents water damage, structural issues, costly repairs, improves energy efficiency, and enhances appearance. Pricing: Typically $800–$2,500 based on size, flue count, and materials; one-time long-lasting fix. Close confidently: Recommend scheduling soon to stop damage; ask when to start. Tech tip: Educate customers early—chase covers prevent costly damage often unnoticed until too late. Refractory Panel Replacement – Quick Sales Summary Explain panels: Fire-resistant liners inside prefab fireplaces that protect firebox and surrounding framing. Show the problem: Cracked, warped, or broken panels cause heat loss, water intrusion, and safety risks. Present solution: Remove damaged panels and install new UL-listed, heat-resistant panels made for prefab units. Highlight benefits: Restores safety and appearance, prevents damage, extends fireplace lifespan. Pricing: $700–$3,000 depending on firebox size and materials; one-time lasting repair. Close confidently: Recommend scheduling soon to ensure safe operation; ask when to start. Tech tip: Stress safety and performance; educate customers on risks and importance of timely repair. Glass Door Installation – Quick Sales Summary Explain what they are: Tempered glass doors that cover the fireplace opening, control airflow, and add safety. Show the problem: Without doors, sparks can escape, increasing fire risk; open fireplaces lose heat and reduce energy efficiency. Present solution: Install glass doors to contain sparks, protect home and family, reduce drafts, and improve efficiency. Highlight benefits: Enhances safety, lowers energy bills, adds elegant look, and is easy to use and maintain. Pricing: Typically $900–$2,300 depending on size and style; one-time value upgrade. Close confidently: Recommend scheduling to improve safety, efficiency, and appearance; ask when to start. Tech tip: Emphasize the combo of safety, comfort, and style as a smart, practical upgrade. ricket Installation – Quick Sales Summary Explain what it is: Small pitched structure behind chimney that diverts water away to prevent pooling. Show the problem: Missing cricket causes water buildup, leaks, wood rot, mold, and damage around chimney and roof. Present solution: Install durable, weather-resistant cricket to protect chimney base and roof structure. Highlight benefits: Prevents leaks, mold, costly repairs; extends roof life by improving drainage. Pricing: Typically $2,000–$4,000 depending on size and materials; smart investment to avoid bigger problems. Close confidently: Recommend scheduling soon to protect chimney and roof; ask when to start. Tech tip: Educate customers about this less-known but code-recommended upgrade and focus on preventing water damage. Pilot Light Repair/Installation – Quick Sales Summary Explain what it is: Small, constantly burning flame that lights the main burner in gas fireplaces or heaters. Show the problem: Pilot light out, damaged, or not staying lit causes fireplace to fail or shut off, creating safety and comfort issues. Present the solution: Repair or install a new pilot assembly to ensure reliable ignition and operation, following safety standards. Highlight benefits: Ready-to-use fireplace, improved safety by preventing gas buildup, clean ignition, fewer unexpected shut-offs, extends unit lifespan. Pricing: Typically $850–$1,600 depending on parts and access; simple fix restoring full safety and function. Close confidently: Recommend servicing now to keep fireplace safe and reliable; ask when to schedule. Tech tip: Emphasize pilot light’s critical role and help customers understand how this small fix keeps their whole system working safely. Siding Repair – Quick Sales Summary Explain what siding is: Exterior material protecting home from weather, moisture, pests, and giving a finished look. Show the problem: Cracked, warped, or loose siding lets water, pests in—causing rot, mold, and structural damage. Present the solution: Repair or replace damaged siding, match existing exterior, and seal properly for seamless protection. Highlight benefits: Keeps moisture and pests out, preserves appearance, prevents bigger damage, protects investment and resale value. Close confidently: Recommend scheduling repair soon to keep home safe, dry, and attractive; ask when to start. Tech tip: Emphasize siding repair as vital maintenance to avoid costly problems and preserve home’s value. Siding Replacement – Quick Sales Summary Explain siding: Outer protective layer shielding home from weather, moisture, pests, and giving style. Show the problem: Severely cracked, warped, faded, or damaged siding can’t protect properly; replacement needed. Present solution: Remove old siding and install high-quality, durable new materials for lasting protection and modern look. Highlight benefits: Protects from damage, improves insulation and energy efficiency, boosts curb appeal and property value, requires less maintenance. Close confidently: Recommend scheduling replacement soon to restore protection and enhance appearance; ask when to start. Tech tip: Emphasize siding replacement as a smart investment in home protection, comfort, and long-term value. Flashing Replacement – Quick Sales Summary Explain flashing: Metal barrier sealing the joint where chimney meets roof to keep water out. Show the problem: Rusted, pulled-away, or cracked flashing causes leaks, water stains, rot, and mold near chimney. Present solution: Remove damaged flashing and install new, high-quality metal flashing, sealed tightly for watertight protection. Highlight benefits: Stops leaks, prevents costly damage, protects roof and structure, strengthens roofing system. Close confidently: Recommend scheduling replacement soon to protect home long-term; ask when to start. Tech tip: Stress flashing replacement as critical, not cosmetic; explain how it prevents major future damage and saves money. Gas Pipe Replacement – Quick Sales Summary Explain gas pipes: Deliver natural gas or propane to fireplaces/appliances for ignition and operation. Show the problem: Rusted, corroded, or loose pipes can cause gas leaks, uneven flames, smells, or failure to ignite. Present solution: Remove old pipe and install new, certified piping, sealed and pressure-tested for safety and code compliance. Highlight benefits: Eliminates leak and fire risks, prevents carbon monoxide exposure, restores safe, efficient, and reliable operation. Close confidently: Recommend scheduling replacement soon to protect home and ensure safety; ask when to start. Tech tip: Emphasize this as a crucial safety upgrade that customers often overlook until a problem arises. Smoke Chamber Parging – Quick Sales Summary Explain smoke chamber: Sloped area above firebox guiding smoke smoothly into chimney flue. Show the problem: Cracks, gaps, or rough surfaces disrupt smoke flow, reduce draft, allow smoke/gas leaks, increase creosote buildup and fire risk. Present solution: Apply fire-resistant mortar to smooth and seal chamber walls, restoring safe smoke flow and chimney function. Highlight benefits: Prevents leaks, improves draft efficiency, reduces creosote buildup, lowers chimney fire risk, extends chimney life. Close confidently: Recommend scheduling soon to keep chimney safe and efficient; ask when to start. Tech tip: Educate customers on this often-overlooked safety upgrade and its critical role in preventing fire hazards. Standard Chimney Cap Installation – Quick Sales Summary Explain what it is: Metal cover on top of flue preventing rain, debris, and animals from entering while allowing smoke to vent. Show the problem: No or damaged cap lets water damage liner and ceilings, debris block flue, animals nest inside—causing fire and ventilation hazards. Present solution: Install standard chimney cap—quick, affordable protection that extends chimney life. Highlight benefits: Prevents water damage, keeps out debris and animals, supports draft efficiency, durable and low maintenance. Close confidently: Recommend installation to protect chimney and reduce future maintenance; ask when to schedule. Tech tip: Emphasize this simple, valuable upgrade as essential for chimney protection and safety. The Sale Starts at the Door – Key Points Summary First Impressions Matter You’re the face of A1 Chimney from the moment you arrive. Clean, tucked uniform; organized, clean truck; all tools ready. A clean appearance equals a professional job in the customer’s eyes. Confident Arrival Approach confidently with a smile, eye contact, and stand tall. Use warm, clear greetings like: “Good morning! I’m Mike with A1 Chimney. I’m here for your inspection today...” Avoid casual or lazy greetings. Establish Control & Comfort Speak confidently but be approachable. Use the A1 process: greet, introduce, explain, invite customer to join or wait comfortably. Positive Body Language Stand upright, hands out of pockets, smile, make eye contact. Avoid slouching, chewing gum, phone distractions, or looking rushed. Build Rapport Quickly Ask genuine, simple questions: “How long have you lived here?” “Have you used the fireplace a lot this season?” “Any issues you’ve noticed before I get started?” Key Phrases at the Door Explain inspection steps clearly: taking notes/photos, providing a detailed report with pictures and codes, so customer fully understands findings. Common Mistakes to Avoid Don’t park on lawns or block driveways. Always wear shoe covers before entering. Don’t rush intros; speak clearly and calmly. Avoid phone use or distracted behavior when arriving. Closing Reminder Remember, you represent the company at first contact. Make the first minute count to build trust and set a positive tone for the whole job. Quick Tech Sales Outline: The Sale Starts at the Door First Impression: Clean, tucked uniform; organized truck; all tools ready. Confident walk, smile, eye contact, stand tall. Greeting: Use clear, professional opening lines (e.g., “Good morning, I’m here for your chimney inspection.”) Avoid casual or lazy greetings. Set the Tone: Speak confidently but be approachable. Briefly explain inspection process and report delivery. Body Language: Stand upright, hands visible, smile, avoid distractions like phones or gum. Build Rapport: Ask simple, genuine questions to engage customer. Avoid Mistakes: Don’t park on lawns or block driveways. Always use shoe covers before entering. Don’t rush intro or seem distracted. Remember: You represent the company—first impressions build trust and ease the sales process. The Walkthrough & Inspection – Quick Tech Outline Prepare before presenting: Have full inspection report and two estimates ready (urgent repairs & full system fix). Presenting two options guides customers toward a balanced choice naturally. Present professionally: Sit down with customer, show report with photos and code notes on tablet. Explain both estimates clearly and emphasize customer choice. Use simple language & visuals: Avoid jargon; explain issues with clear photos. Example: “This metal around your chimney is loose and letting water in.” Connect issues to real risks: Explain consequences without scaring (e.g., mold, carbon monoxide, structural damage). Offer recommendations confidently: Present at least two options (good/better). Mention maintenance memberships if applicable. Give customer space: Allow time to review report and ask questions; avoid rushing for a decision. Wrap up without pressure: Summarize findings, safety standards, and offer to start work while onsite. Emphasize honesty and professionalism build trust. Tech quick tips: Be organized and confident Show clear, labeled photos Explain simply and relate to safety/damage Offer choices, never pressure How to Recommend Repairs Effectively – Quick Tech Guide Focus on value, not just cost: Emphasize peace of mind, safety, and protection. Example: “Sealing the crown prevents costly water damage and comes with a 5-year warranty.” Avoid just quoting prices without context. Use “professional pressure” without pushing: Recommend same-day repairs when trained and equipped. Say: “We can handle this now to save you a second trip and extra fee.” For bigger jobs, explain certified teams will follow up. Speak to safety & long-term benefits: Tie repairs to code compliance and preventing expensive future damage. Example: “This brings your system up to NFPA-211 standards and prevents $3,000+ repairs.” Handle silence confidently: After recommending, pause and let the customer think. Example: “Take a moment to review while I clean up. I’m here if you have questions.” Answer questions, not objections: Respond clearly to pricing, warranty, or timing questions. Example: “Price includes materials, sealing, 5-year warranty, and full documentation.” Offer add-ons and membership plans: Mention annual maintenance memberships for safety and discounts. Builds trust and recurring revenue. Final recap: Don’t oversell or sound desperate. Explain the repair and benefits calmly and professionally. Give options (urgent vs full), show value with photos and codes, recommend confidently, offer same-day work when possible, and mention warranties/memberships. Handling Inspection-Only Clients – Key Points Start normally: Be professional, build rapport, inspect visually as usual. Identify blocker: Notice and point out soot/debris blocking clear flue inspection. Educate: Explain Level 2 inspection requires clear flue interior, which means cleaning is necessary. Remove objection: Clarify that a valid, code-compliant report requires cleaning to see hazards, and partial reports aren’t legally valid. Offer to proceed: Suggest same-visit cleaning to complete Level 2 inspection and deliver full report promptly. Tone: Stay calm, confident, clear, and pressure-free. Recap: Inspections must be done right; explain cleaning protects client and ensures valid documentation. Working with Budget-Conscious Clients – Key Points Start small: Clients may want the cheapest or bare minimum option. Get them to say yes to the most essential, affordable repair first. Understand mindset: Clients may have tight budgets, be unsure of company, or just want to pass inspection. Avoid pushing big-ticket repairs upfront. Set honest expectations: Explain estimates can change if unforeseen issues arise during the job. Always communicate changes before proceeding. Build trust on-site: Clients who approve small repairs are more likely to approve larger work later. Show professionalism, educate with photos, and explain why early fixes save money. Use real-world examples: Start with a standard repair estimate (e.g., liner install). Update scope and price if complications arise during the job. Final tip: Close on the essential, affordable item first. Trust built through doing the first job often leads to bigger approvals without pressure. Handling Downdraft Issues – Key Points What is a downdraft? Air flows down the chimney instead of up, pushing smoke back inside. Causes include wind, negative house pressure, short or misplaced chimney, blocked or cold flue, missing/damaged cap. Signs to look for: Smoke fills room after lighting fire Cold drafts when fireplace not in use Ash/soot blown back into room Smoke smell without recent fire Explain to customer: Describe downdraft as air pushing down chimney due to pressure or chimney issues. Assure them it’s usually fixable. Recommended solutions: Start with cleaning the flue (blocked flues worsen downdrafts). Install draft-increasing or vacuum caps. Sometimes extend flue height or address house pressure with vents/makeup air. Never promise a single fix; solve step-by-step. Set expectations: Cleaning plus draft cap fixes most cases (~90%). Further investigation if problem persists. Final tip: Explain clearly, start simple, set realistic expectations, build trust through solution process. | 0 |  | 4385257989
9807833735 | Dispatcher Final Exam | Update |  | Bar Ohayon | 13/August/2025 08:36:32 AM | Hi Jose, I have created a final quizz for the Dispatcher course and I need you to insert the questions and answers. Please do it first thing in the morning then we can let our new dispatcher start with this. Thank you. Dispatcher Final Exam.docx | 1 | 2350034675 | 4398934611
9923393777 | Topics for Chapter 3 | Update |  | Chaim Perez | 28/August/2025 03:09:52 PM | masonry fireplace inspection level 1 - Masonry ( Only how to do ) inspection level 2 - Masonry ( Only how to do ) chimney sweep masonry ( Only how to do ) Fireplace Crack Repair - Both Smoke chamber parge - Both PreFab- Fireplace inspection level-1 ( Only how to do ) inspection level 2 ( Only how to do ) chimney sweep ( Only how to do ) Panel Replacment- Both Wood Stove chimney sweep ( Only how to do ) wood stove inspection ( Only how to do ) Furnace furnace inspection ( Only how to do ) General cap installation ( Custom ) - Both cap Installation ( standard size ) - Both Damper Cap Installation - Both crown repair - both crown replacement Both brick water proofing Both flashing repair Both flashing replacement Both liner installation Both heatshield process Both chase cover installation Both Glass door Installation Both Cricket Installation - Both Siding repair & replacement- Both Gas gas log installation Both gas System Troubleshooting ( Only how to do ) pilot light replacement & Gas Valve removal - Both remote installation only how to do Thermocouple only how to do Gas Valve only how to do | 0 |  | 4441723333
10063754760 | Duplicate A1 Chimney | Update |  | Bar Ohayon | 16/September/2025 12:38:18 PM | Phone Number: (888) 788-4412 Subdomain: NY We need the following areas: Brooklyn Queens Long Island Manhatten Yonkers | 0 |  | 4495208000
10063754760 | Duplicate A1 Chimney | Update |  | Bar Ohayon | 18/September/2025 01:00:53 PM | We need to add this address: 3100 47th Ave #378, Long Island City, NY 11101 | 0 |  | 4502987952
10085155785 | New Website - Emergency Plumbing | Update |  | Bar Ohayon | 18/September/2025 03:18:36 PM | Siteground access same as gmail Please build this website same as emergencyaccorp.com Emergency Plumbing.txt | 0 | 2429253007 | 4503553709
10673287159 | Websites Changes: A1 Chimney Sweep ¦ Ace Fireplace | Update |  | Shoval Ohayon | 01/December/2025 12:27:51 PM | Add Description somewhere in the website showing that we are lead generation company that will get the best chimney sweeeper in their area. | 0 |  | 4714066993
10731479120 | US Chimney Supply Website | Update |  | Shoval Ohayon | 16/December/2025 09:43:28 AM | One demo purchase needed for trade mark | 0 |  | 4757252384
10731479120 | US Chimney Supply Website | Update |  | Bar Ohayon | 23/December/2025 04:01:28 PM | Gmail info@uschimneysupply.com US#chimS@2025 Shopify: Login with google Please fix design and make it look better and make a purchasing test with test item of $1 thank you. | 1 |  | 4776534815
18226568771 | A1 Chimney - New Subdomains | Update |  | Bar Ohayon | 20/October/2025 03:41:36 PM | New Subdomains: mo (Missouri) (888) 839-9114 800 E 101st Terrace #347, Kansas City, MO 64131 ok (Oklahoma) (888) 711-5597 10401 W Reno Ave #105, Oklahoma City, OK 73127 or (Oregon) (888) 419-9997 555 SE Martin Luther King Jr Blvd #3071, Portland, OR 97214 wa (Washington) (888) 261-1666 1601 5th Ave #1035, Seattle, WA 98101 sf (San Francisco) (888) 520-0075 1390 Market Street #2018, San Francisco, CA 94102 ri (Rhode Island) (888) 668-5662 10 Dorrance St #719, Providence, RI 02903 1. Add those locations to the store locator on the main website. 2. Add these addresses to the actual city page and change the author to "Location City". 3. Create a location page for each location 4. Add location section to Home and Our Locations page. | 0 |  | 4595317805
18226568771 | A1 Chimney - New Subdomains |  | Reply | Bar Ohayon | 20/October/2025 03:49:36 PM | Greater Oklahoma City.txt Greater San Francisco.txt Greater Kansas City.txt | 0 | 2497807275,2497807277,2497807283 | 4595342073 | 4595317805
18226568771 | A1 Chimney - New Subdomains |  | Reply | Bar Ohayon | 20/October/2025 03:49:51 PM | I need you to get lists for the rest | 0 |  | 4595342726 | 4595317805
18226638987 | Locations section | Update |  | Bar Ohayon | 20/October/2025 03:51:40 PM | Hi Jose, Please add the locations section to mn.a-1chimney.com, with this address: 121 N Washington Ave #320B, Minneapolis, MN 55401 You can get the section from one of the other subdomains (DFW, CLE, NJ, etc...). Thank you. | 0 |  | 4595348111
18381454879 | New Emails | Update |  | Bar Ohayon | 17/November/2025 12:45:42 PM | Please create for me the following emails and send me here the passwords and the backup codes: office@stl.a-1chimney.com office@gso.a-1chimney.com office@clt.a-1chimney.com office@kci.a-1chimney.com office@ok.a-1chimney.com office@or.a-1chimney.com office@wa.a-1chimney.com office@mn.a-1chimney.com office@sf.a-1chimney.com office@ri.a-1chimney.com Thank you. | 0 |  | 4676908670
18381454879 | New Emails |  | Reply | Jose Demasi | 17/November/2025 01:49:46 PM | office@stl.a-1chimney.com = *PHnT79yaTDU5gP* 19697485, 72777971, 14859866, 73902733, 52389690, 23026040, 45921840, 47875664, 63103882, 75134865 office@gso.a-1chimney.com = 9nWK86e5qEUd7eS% 09724321, 79592941, 75947346, 69631135, 44891101, 42177234, 21402035, 97729785, 61050335, 27809828 office@clt.a-1chimney.com = 3Gj>L%XKa%mg3uA* 41702782, 04319570, 00767827, 35255343, 08329263, 47778451, 59309975, 05437508, 12983093, 52220952 office@kci.a-1chimney.com = <R%FSqQRXuCA8uT= 89615721, 10244938, 38508098, 61266803, 22484697, 14863818, 64245167, 99288768, 88985191, 99972735 office@ok.a-1chimney.com = LZ<Gur8E75dr7hT< 49927890, 90960744, 49095263, 86071397, 23823696, 89417699, 24727340, 77288064, 07870982, 62931504 office@or.a-1chimney.com = dFLKJHeBmXDT8nX* 49486865, 98457338, 52158823, 23750134, 25729103, 03687098, 63438049, 04917262, 72174657, 99314920 office@wa.a-1chimney.com = 2ENGCdha6hdT4nM> 05744795, 67852111, 55640101, 54651924, 69951601, 29592780, 10893351, 21952327, 67768794, 89066909 office@sf.a-1chimney.com = uyLqHSuZN>uJ8mN= 05263487, 05063736, 44631066, 96495418, 98312899, 21951487, 99614106, 59237612, 44563562, 51355514 office@ri.a-1chimney.com = aD2N<jHJ*dWN8nE* 57944358, 41528450, 75292879, 47958543, 58460354, 73703875, 91105438, 06682156, 30102415, 92466375 | 0 |  | 4677154361 | 4676908670
18381454879 | New Emails | Update |  | Bar Ohayon | 17/November/2025 01:10:24 PM | (314) 887-5088 (336) 777-5575 (980) 486-8488 (816) 766-0466 (405) 775-9795 (503) 877-6500 (206) 274-5977 (612) 444-3145 (415) 651-3441 (401) 600-3800 | 0 |  | 4677004220
18381454879 | New Emails |  | Reply | Bar Ohayon | 17/November/2025 01:10:35 PM | 100 S 4th St #549, St Louis, MO 63102 - STL 516 W Friendly Ave #108, Greensboro, NC 27401 - GSO 128 S Tryon St #1818, Charlotte, NC 28202 - CLT 800 E 101st Terrace #347, Kansas City, MO 64131 - KCI 10401 W Reno Ave #105, Oklahoma City, OK 73127 555 SE Martin Luther King Jr Blvd #3071, Portland, OR 97214 1601 5th Ave #1035, Seattle, WA 98101 121 N Washington Ave #320B, Minneapolis, MN 55401‭ 1390 Market St #2018, San Francisco, CA 94102 10 Dorrance St #719, Providence, RI 02903 | 0 |  | 4677004785 | 4677004220