## toula elwell
Toula Elwell
Open Tasks
Name | Subitems | Person | Status | Priority | Due Date | Date | Item ID (auto generated)
Ahrefs Setup |  | Jose Demasi | Working on it | High |  |  | 10873851197
SEO Score Improvement | Us Garage Repair,A-1 Garage Door Repair,Premier Garage Repair,Crestline,Air 75,Top Up Roofing,Us Garage Door Repair,Emergency Plumbing Corp,Energy Builder Group | Jose Demasi | Received | Medium |  |  | 10874346173
Subitems | Name | Owner | Category | Status | Date | Item ID (auto generated)
| Us Garage Repair |  |  |  |  | 10874347344
| A-1 Garage Door Repair |  |  |  |  | 10874341548
| Premier Garage Repair |  |  |  |  | 10874341545
| Crestline |  |  |  |  | 10874331283
| Air 75 |  |  |  |  | 10874341547
| Top Up Roofing |  |  |  |  | 10874341099
| Us Garage Door Repair |  |  |  |  | 10874331860
| Emergency Plumbing Corp |  |  |  |  | 10874347203
| Energy Builder Group |  |  |  |  | 10874341741
Create Address Pages for All Subdomains | A1 Garage Door Repair,US GARAGE REPAIR,A1 Chimney,Speedy garage doors,Premier Garage Repair,Crestline | Jose Demasi | Working on it | Medium |  |  | 10874158984
Subitems | Name | Owner | Category | Status | Date | Item ID (auto generated)
| A1 Garage Door Repair |  | Done | Done |  | 10936242033
| US GARAGE REPAIR |  | Done | Done |  | 10936237089
| A1 Chimney |  | Stuck | Stuck |  | 10936232118
| Speedy garage doors |  | Done | Done |  | 10936426425
| Premier Garage Repair |  | Done | Done |  | 10937478100
| Crestline |  | Working on it | Working on it |  | 10948912522
Drive Folder Buildup |  | Jose Demasi | Stuck | Medium |  |  | 10874495923
Check Mobile Responsiveness | Us Garage Repair,A-1 Garage Door Repair,Premier Garage Repair,Crestline,Air 75,Top Up Roofing,Us Garage Door Repair,Emergency Plumbing Corp,Energy Builder Group | Jose Demasi | Received | Low |  |  | 10873129020
Subitems | Name | Owner | Category | Status | Date | Item ID (auto generated)
| Us Garage Repair |  |  |  |  | 10874001598
| A-1 Garage Door Repair |  |  |  |  | 10874023513
| Premier Garage Repair |  |  |  |  | 10874006348
| Crestline |  |  |  |  | 10874006198
| Air 75 |  |  |  |  | 10874023365
| Top Up Roofing |  |  |  |  | 10874001062
| Us Garage Door Repair |  |  |  |  | 10874000605
| Emergency Plumbing Corp |  |  |  |  | 10874000297
| Energy Builder Group |  |  |  |  | 10873998930
Readibility Score Improvement | Us Garage Repair,A-1 Garage Door Repair,Premier Garage Repair,Crestline,Air 75,Top Up Roofing,Us Garage Door Repair,Emergency Plumbing Corp,Energy Builder Group | Jose Demasi | Received | Low |  |  | 10874394576
Subitems | Name | Owner | Category | Status | Date | Item ID (auto generated)
| Us Garage Repair |  |  |  |  | 10874384554
| A-1 Garage Door Repair |  |  |  |  | 10874357179
| Premier Garage Repair |  |  |  |  | 10874386378
| Crestline |  |  |  |  | 10874372194
| Air 75 |  |  |  |  | 10874371990
| Top Up Roofing |  |  |  |  | 10874357643
| Us Garage Door Repair |  |  |  |  | 10874384578
| Emergency Plumbing Corp |  |  |  |  | 10874357082
| Energy Builder Group |  |  |  |  | 10874375171
Make sure each team page is updated in A1 chimney sub domains |  | Jose Demasi | Received | Low |  |  | 10881053796
Everdoors Website Design |  | Jose Demasi | Received | On Hold |  |  | 10874530608
Completed Tasks
Name | Subitems | Person | Status | Priority | Due Date | Date | Item ID (auto generated)
Fix Incorrect Address - Crestline MD |  | Jose Demasi | Done | Critical ⚠️️ |  |  | 10880462173
Design New Watermark for Air 75 |  | Jose Demasi | Done | Low |  |  | 10873227767
A1 Chimney Website - Our Team |  | Jose Demasi | Done | Low |  |  | 10874426145
Use new watermarks in Air 75, replace all existing ones |  | Jose Demasi | Done | High |  |  | 10881895214
Configure websites in a1 tools |  | Jose Demasi | Done | High |  |  | 10910325973
Training Videos | Watch Website Basic Videos on Drive,Watch City Pages Video on Drive,Watch Website Migration Video on Drive | Jose Demasi | Done | Low |  |  | 10874099361
Subitems | Name | Owner | Category | Status | Date | Item ID (auto generated)
| Watch Website Basic Videos on Drive |  | Done | Done |  | 10874113519
| Watch City Pages Video on Drive |  | Done | Done |  | 10874108994
| Watch Website Migration Video on Drive |  | Done | Done |  | 10874125231
Crestline Subdomains - Fix errors found on subdomains homepage |  | Jose Demasi | Done | Medium |  |  | 10914723755
Crestline Subdomains - Check Mobile Responsiveness and Fix |  | Jose Demasi | Done | Medium |  |  | 10880789410
Website Familiarity |  | Jose Demasi | Done | Medium |  |  | 10874644946
Configure passwords for configured websites in a1tools |  | Jose Demasi | Done | High |  |  | 10922049143
Check All Addresses & Phone Numbers | US Garage Repair,A-1 Garage Door Repair,Premier Garage Repair,Crestline,Air 75,Top Up Roofing,US Garage Door Repair,Emergency Plumbing Corp,Energy Builder Group | Jose Demasi | Done | High |  |  | 10872789781
Subitems | Name | Owner | Category | Status | Date | Item ID (auto generated)
| US Garage Repair |  | Done | Done |  | 10874009017
| A-1 Garage Door Repair |  | Done | Done |  | 10874018429
| Premier Garage Repair |  | Done | Done |  | 10874043557
| Crestline |  | Done | Done |  | 10874016697
| Air 75 |  | Done | Done |  | 10874043840
| Top Up Roofing |  | Done | Done |  | 10874051537
| US Garage Door Repair |  | Done | Done |  | 10874024775
| Emergency Plumbing Corp |  | Done | Done |  | 10874020923
| Energy Builder Group |  | Done | Done |  | 10874020889
Remove Air 75 License from Website |  | Jose Demasi | Done | Critical ⚠️️ |  |  | 10980193187
Recurring Tasks
Name | Subitems | Person | Status | Priority | Due Date | Date | Item ID (auto generated)
Daily Performance |  | Jose Demasi | Permanent | Low |  |  | 10872733839
Blog Posts for Every Website |  | Jose Demasi | Weekly | High |  |  | 10872713608
Plugin Update |  | Jose Demasi | Weekly | Low |  |  | 10874716553
Ahrefs Crawls |  | Jose Demasi | Monthly | Medium |  |  | 10872793272
Check Mobile Responsiveness for Every Website |  | Jose Demasi | Monthly | Low |  |  | 10873130282
Guidelines
Name | Subitems | Person | Status | Priority | Due Date | Date | Item ID (auto generated)
Website Basics |  | Jose Demasi | Guidelines | None |  |  | 10873095677
Migration Basics |  | Jose Demasi | Guidelines | None |  |  | 10873142273
Website Users |  | Jose Demasi | Guidelines | None |  |  | 10874242244
Website Plugins |  | Jose Demasi | Guidelines | None |  |  | 10874280035
Company Files and Access
Name | Subitems | Person | Status | Priority | Due Date | Date | Item ID (auto generated)
Passwords |  | Jose Demasi | Files | None |  |  | 10872736541
Employment Agreement |  | Jose Demasi | Files | None |  |  | 10872764850
Website Users and Passwords |  | Jose Demasi | Files | None |  |  | 10874257545

## toula elwell-updates
Toula Elwell | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
10872713608 | Blog Posts for Every Website | Update |  | Toula Elwell | 30/December/2025 10:36:54 AM | Speedy Garage Doors Week 1 Done | 0 |  | 4785542849
10872713608 | Blog Posts for Every Website | Update |  | Toula Elwell | 30/December/2025 10:41:27 AM | https://www.usgaragerepair.net/ Week 1 Done | 0 |  | 4785555169
10872713608 | Blog Posts for Every Website | Update |  | Toula Elwell | 30/December/2025 10:42:52 AM | https://www.a-1garagedoorrepair.com/wp-admin/edit.php week 1 done | 0 |  | 4785564588
10872713608 | Blog Posts for Every Website | Update |  | Toula Elwell | 30/December/2025 01:50:44 PM | https://www.us-garagedoorrepair.com/wp-admin/edit.php week 1 done | 0 |  | 4786203800
10872713608 | Blog Posts for Every Website | Update |  | Toula Elwell | 30/December/2025 03:58:47 PM | https://www.premiergaragerepair.net/wp-admin/post.php?post=3665&action=edit week 1 done | 0 |  | 4786714575
10872713608 | Blog Posts for Every Website | Update |  | Toula Elwell | 31/December/2025 10:59:25 AM | https://www.a-1chimney.com/wp-admin/post.php?post=6840&action=edit week 1 done | 0 |  | 4788023364
10872713608 | Blog Posts for Every Website | Update |  | Toula Elwell | 31/December/2025 11:07:47 AM | https://www.topuproofing.com/roof-inspection-checklist/ week 1 done | 0 |  | 4788044306
10872713608 | Blog Posts for Every Website | Update |  | Toula Elwell | 02/January/2026 02:42:30 PM | Week one completely done for every website!! Finished >* https://www.air75hvac.com/hvac-zoning-systems-right-for-your-home/ today | 0 |  | 4792303627
10872713608 | Blog Posts for Every Website | Update |  | Toula Elwell | 08/January/2026 03:14:28 PM | week 2 done: A1 CHIMNEY - https://www.a-1chimney.com/blog/chimney-repair-article/ | 0 |  | 4814431299
10872713608 | Blog Posts for Every Website | Update |  | Toula Elwell | 08/January/2026 03:14:50 PM | week 2 done: A1 Garage Door Repair - https://www.a-1garagedoorrepair.com/garage-door-making-grinding-noise/ > | 0 |  | 4814432969
10872713608 | Blog Posts for Every Website | Update |  | Toula Elwell | 08/January/2026 04:25:14 PM | week 2 done: Air 75 HVAC - https://www.air75hvac.com/hvac-short-cycling/ | 0 |  | 4814713411
10872713608 | Blog Posts for Every Website | Update |  | Toula Elwell | 09/January/2026 11:28:08 AM | >* Finished working on the weekly blog posts task for week 2 FINISHED: >* A1 CHIMNEY - https://www.a-1chimney.com/blog/chimney-repair-article/ * A1 Garage Door Repair - https://www.a-1garagedoorrepair.com/garage-door-making-grinding-noise/ * Air 75 HVAC - https://www.air75hvac.com/hvac-short-cycling/ * Speedy Garage Doors - https://www.speedygaragedoors.com/garage-door-problems-homeowners-ignore/ * US Garage Door Repair - https://www.us-garagedoorrepair.com/garage-door-services-matter/ * Us Garage Repair - https://www.usgaragerepair.net/garage-door-services-matter/ * Premier Garage Repair - https://www.premiergaragerepair.net/garage-door-balance-issues/ * Crestln - https://www.crestln.com/roof-ventilation-problems/ | 0 |  | 4817007777
10872733839 | Daily Performance | Update |  | Toula Elwell | 30/December/2025 04:51:13 PM | I reviewed several HVAC company websites to see how they handle blog thumbnails and watermarks, and many didn’t use blogs or thumbnails at all. I worked on multiple watermark/thumbnail designs for Air 75, creating three versions in total. After each version, I checked in with Jose for feedback, which led to the final design. I also collaborated with Jose to get all required applications set up on my computer since the new screen arrived today. Additionally, I researched watermark design ideas for inspiration. I completed five blog posts today as well. I also recreated two watermarks in Figma to finish the blog posts. Wrote out content for 2 more blog posts, need to get one all green seo wise, and both the watermark image. After that have 1 more blog post to write for the week. | 0 |  | 4786847779
10872733839 | Daily Performance | Update |  | Toula Elwell | 31/December/2025 04:18:05 PM | What I did today, did revisions of the air 75 watermark as jose wanted checking after each revision, he needed a service and blog revision. I finished a final product. I also finished making the blog posts for every website but didn't submit the air 75 one yet as i need to change all watermarks to the new one once jose finished that watermark phone number changer application in a1 tools, the tool is currently being fixed by jose. Finished the A1 Chimney Website - Our Team task where I addeed my own picture into the website and my o0wn name and title and removed 2 people that aren't working here anymore. I also completed the critical task fix incorrect address - crestline md as soon as i saw it when jose added it and told me about it. I ensured each page that shouldn't change the other slugs that weren't MD that the search and replace didn't change their address and learned from jose what to do if the search and replace method doesn't work, I edidted in wordpress elementor on my own but jose showed me I can also use phpmyadmin. I also learned how to roll back changed in wordpress through the revisions link in wordpress as jose showed me since our lesson yesterday when doing search and replace messed up a page, we fixed that together. I also completed most of the check all addresses and phone numbers task in the excel sheet, I ensured that a-1 garage door repair, cresitne, air 75, top up roofing, us garage door repair, emergency plumbing corp. If a slug wasn't in the excel sheet I added it with the websites correct information. I am on hold for us garage repair, premier garage repair, and energy builder corp. The first two because jose is correcting and making a tool for me to use to change all the phone numbers on the watermarks. The last one because I doin't have the link to the last ones website as jose deleted that link yesterday to not confuse me with another task i did yesterday. I have downloaded images for us garage repair pa and am waiting to test the app when jose finished correcting the code. An additional thing i did was recreate the thumbnail for top up roofing as jose is missing the photoshop watermark for it and i needed to make the blog post for that company, i double checked with jose and he said it looked good and to try photoshop instead of figma next time when i need to. To finish off the day I started the Ahrefs Setup task and have been adding websites to href and crawling them, I posted update an hour early and am working on this task till 5pm today | 0 |  | 4788762245
10872733839 | Daily Performance | Update |  | Toula Elwell | 05/January/2026 09:10:51 AM | 1/2/2026 >* Plugin Update on every website * Using new watermarks I made in Air 75, replaced all existing ones * Week 1 Blogs Completely Done: Finished last one today - https://www.air75hvac.com/hvac-zoning-systems-right-for-your-home/ * I got help from Jose figuring out how to change the popup image on WordPress * Finished checking all addresses and phone numbers in each page except the energy builder group page as that's the one I don't have a link too and am waiting on Jose to provide the sitemaps link to that page. * Changed phone numbers in PA US Garage Repair watermarks to the correct phone number using the tool Jose provided * Changed phone numbers in PA Premier Garage Repair watermarks to the correct phone number using the tool Jose provided * Working on the Ahrefs Setup task where I am adding all the Website for Analytics, Adding Meta Tags to Homepage to Verify, and Running Crawls and Verify Issues: added TopUp Roofing, added Air75hvac, working on A-1 Chimney | 0 |  | 4798104358
10872733839 | Daily Performance | Update |  | Toula Elwell | 05/January/2026 04:51:05 PM | 1/5/2026 >* Working on the Ahrefs Setup task where I am adding all the Website for Analytics, Adding Meta Tags to Homepage to Verify, and Running Crawls: added crestline and its slugs, finished premier garage repair slugs, finished A1 Chimney slugs, finished adding speedy garage doors and their slugs, finished adding a1 garage door repair and their slugs, finished adding us garage repair slugs * I am stuck on Ahrefs Setup task, I did everything but verify issues and have no idea whether verify means solve or record whats broken * Finished Working and finished on training videos task: finished Watching Website Basic Videos on Drive - contact us, featured image, header and site setting,why chose us, and wordpress setup, finished Watch City Pages Video on Drive, finished, Watch Website Migration Video on Drive * Working on and finished: Configured websites in a1 tools task as jose requested * got my sitegrounds account set up by jose * Someone who wasn't Jose and wasn't me broke some websites with an image so I went through and restored those websites to a previous version * Finished Crestline Subdomains - Fix errors found on subdomains homepage Task. * Working on Crestline Subdomains - Check Mobile Responsiveness and Fix period. | 0 |  | 4800820836
10872733839 | Daily Performance | Update |  | Toula Elwell | 06/January/2026 04:57:11 PM | 1/6/2026 >* Working on and just finished the website familiarity task: looked at all our websites and then went and looked at other peoples websites for design inspiration one place being dribble * Jose made mistake regarding the password portion of the configure websites in a1tools task, I am correcting the mistake as requested and am adding the new application password to each website and its subdomain. * Finished Configure passwords for configured websites in a1tools task. * Working on Create Address Pages for All Subdomains task (I need you to create "Address Pages" for each of the Subdomains, in this case ignore the Main Websites. Basically make a new Page with that Subdomain Location's Address as the name, make sure to include: Address. Tagline. Phone Number. Business Description. 4 Images. 3 Provided Services. 2 Locations ( Outbound Links )- City- State- Social Media SHARE links- 4 Services ( Outbound Links )- Hours of operation- Contact Form ): A1 Chimney subdomains minus the ads subdomains STUCK AS I DON'T KNOW THE ADRESSES (https://co.a-1chimney.com/wp-admin/edit.php?post_type=page, https://det.a-1chimney.com/wp-admin/edit.php?post_type=page, https://ct-ads.a-1chimney.com/wp-admin/edit.php?post_type=page, https://co.a-1chimney.com/wp-admin/edit.php?post_type=page, https://dfw-ads.a-1chimney.com/wp-admin/edit.php?post_type=page, https://det.a-1chimney.com/wp-admin/edit.php?post_type=page, https://sac.a-1chimney.com/wp-admin/edit.php?post_type=page, https://de.a-1chimney.com/wp-admin/edit.php?post_type=page, https://ok.a-1chimney.com/wp-admin/edit.php?post_type=page) US GARAGE REPAIR DONE A1 GARAGE DOOR REPAIR IN PROGRESS (https://ga.a-1garagedoorrepair.com/wp-admin/post.php?post=2205&action=elementor, https://ct.a-1garagedoorrepair.com/wp-admin/edit.php?post_type=page) >* Working on and am now stuck on Drive Folder Buildup where I'm Build up the Drive Folder with the Logos of Every Website as well as their Watermark Photoshop Files for Future use. Drive - Websites - Name of Website - Logo. Drive - Websites - Name of Website - Watermark. Make Logo Variations: Grayscale, Inverted Colors, Full White, Full Black. Remake Missing Watermarks A-1 Chimney Done A1 Garage doors done Crestline done Air 75 Done Premier Garage Repair done Speedy Garage Doors Done Us Garage Door Repair STUCK ON EMERGENCY PLUMBING CORP AS I HAVE NO SITEGROUND LINK TO IT STUCK ON TOP UP ROOFING AS I HAVE NO SITEGROUND LINK TO IT | 0 |  | 4806120074
10872733839 | Daily Performance | Update |  | Toula Elwell | 07/January/2026 03:51:10 PM | 1/7/2026 * Working on Create Address Pages for All Subdomains task (I need you to create "Address Pages" for each of the Subdomains, in this case ignore the Main Websites. Basically make a new Page with that Subdomain Location's Address as the name, make sure to include: Address. Tagline. Phone Number. Business Description. 4 Images. 3 Provided Services. 2 Locations ( Outbound Links )- City- State- Social Media SHARE links- 4 Services ( Outbound Links )- Hours of operation- Contact Form ): A1 Chimney subdomains minus the ads subdomains STUCK AS I DON'T KNOW THE ADRESSES (https://co.a-1chimney.com/wp-admin/edit.php?post\_type=page, https://det.a-1chimney.com/wp-admin/edit.php?post\_type=page, https://ct-ads.a-1chimney.com/wp-admin/edit.php?post\_type=page, https://co.a-1chimney.com/wp-admin/edit.php?post\_type=page, https://dfw-ads.a-1chimney.com/wp-admin/edit.php?post\_type=page, https://det.a-1chimney.com/wp-admin/edit.php?post\_type=page, https://sac.a-1chimney.com/wp-admin/edit.php?post\_type=page, https://de.a-1chimney.com/wp-admin/edit.php?post\_type=page, https://ok.a-1chimney.com/wp-admin/edit.php?post\_type=page) US GARAGE REPAIR DONE A1 GARAGE DOOR REPAIR DONE (https://ga.a-1garagedoorrepair.com/303-perimeter-center-north-322-atlanta-georgia-30346/, https://ct.a-1garagedoorrepair.com/20-summer-street-402-stamford-ct-06901/ ) SPEEDY GARAGE DOORS DONE (https://ct.speedygaragedoors.com/100-pearl-street-1458-hartford-ct-06103/, https://ma.speedygaragedoors.com/186-lincoln-st-106-boston-ma-02110/, https://pa.speedygaragedoors.com/100-pearl-street-1458-hartford-ct-06103/ ) PREMIER GARAGE REPAIR SLUGS THAT ARE DONE (https://ct.premiergaragerepair.net/1000-lafayette-blvd-1108-bridgeport-ct-06604/, ma.premiergaragerepair.net/1500-district-ave-2052-burlington-ma-01803) PREMIER GARAGE REPAIR SLUGS THAT ARE IN PROGRESS (https://pa.premiergaragerepair.net/ ) * Working on and am now stuck on Drive Folder Buildup where I'm Build up the Drive Folder with the Logos of Every Website as well as their Watermark Photoshop Files for Future use. Drive - Websites - Name of Website - Logo. Drive - Websites - Name of Website - Watermark. Make Logo Variations: Grayscale, Inverted Colors, Full White, Full Black. Remake Missing Watermarks STUCK ON EMERGENCY PLUMBING CORP AS I HAVE NO SITEGROUND LINK TO IT STUCK ON TOP UP ROOFING AS I HAVE NO SITEGROUND LINK TO IT Improved the phone footer in https://ct.premiergaragerepair.net/1000-lafayette-blvd-1108-bridgeport-ct-06604/ as the margin didn't look even in the original | 0 | 2665802364 | 4810526813
10872733839 | Daily Performance | Update |  | Toula Elwell | 08/January/2026 04:54:13 PM | 1/8/2026 >* Working on and am stuck on the Address Pages for All Subdomains task (I need you to create "Address Pages" for each of the Subdomains, in this case ignore the Main Websites. Basically make a new Page with that Subdomain Location's Address as the name, make sure to include: Address. Tagline. Phone Number. Business Description. 4 Images. 3 Provided Services. 2 Locations ( Outbound Links )- City- State- Social Media SHARE links- 4 Services ( Outbound Links )- Hours of operation- Contact Form ): A1 Chimney subdomains minus the ads subdomains STUCK AS I DON'T KNOW THE ADRESSES (https://co.a-1chimney.com/wp-admin/edit.php?post_type=page, https://det.a-1chimney.com/wp-admin/edit.php?post_type=page, https://ct-ads.a-1chimney.com/wp-admin/edit.php?post_type=page, https://co.a-1chimney.com/wp-admin/edit.php?post_type=page, https://dfw-ads.a-1chimney.com/wp-admin/edit.php?post_type=page, https://det.a-1chimney.com/wp-admin/edit.php?post_type=page, https://sac.a-1chimney.com/wp-admin/edit.php?post_type=page, https://de.a-1chimney.com/wp-admin/edit.php?post_type=page, https://ok.a-1chimney.com/wp-admin/edit.php?post_type=page) US GARAGE REPAIR DONE A1 GARAGE DOOR REPAIR DONE (https://ga.a-1garagedoorrepair.com/303-perimeter-center-north-322-atlanta-georgia-30346/, https://ct.a-1garagedoorrepair.com/20-summer-street-402-stamford-ct-06901/) SPEEDY GARAGE DOORS DONE (https://ct.speedygaragedoors.com/100-pearl-street-1458-hartford-ct-06103/, https://ma.speedygaragedoors.com/186-lincoln-st-106-boston-ma-02110/, https://pa.speedygaragedoors.com/100-pearl-street-1458-hartford-ct-06103/) PREMIER GARAGE REPAIR DONE (https://ct.premiergaragerepair.net/1000-lafayette-blvd-1108-bridgeport-ct-06604/, https://ma.premiergaragerepair.net/1500-district-ave-2052-burlington-ma-01803/, https://pa.premiergaragerepair.net/2-logan-sq-ste-382-philadelphia-pa-19103-2733/) CRESTLN DONE (https://oh.crestln.com/7055-engle-rd-148c-middleburg-heights-oh-44130/) CRESTLN IN PROGRESS (https://il.crestln.com/wp-admin/post.php?post=3470&action=elementor, https://ct.crestln.com/wp-admin/post.php?post=3391&action=edit, https://dc.crestln.com/wp-admin/post.php?post=3225&action=edit, https://nj.crestln.com/wp-admin/post.php?post=3790&action=edit, https://tx.crestln.com/wp-admin/post.php?post=3411&action=edit, https://ga.crestln.com/wp-admin/post.php?post=3318&action=edit, https://ma.crestln.com/wp-admin/post.php?post=2795&action=edit, https://md.crestln.com/wp-admin/post.php?post=3325&action=edit, https://va.crestln.com/wp-admin/post.php?post=3269&action=edit) >* Finished the weekly plugin update task on all websites and their slugs * Working on the weekly blog posts for every website task FINISHED: >* A1 CHIMNEY - https://www.a-1chimney.com/blog/chimney-repair-article/ * A1 Garage Door Repair - https://www.a-1garagedoorrepair.com/garage-door-making-grinding-noise/ * Air 75 HVAC - https://www.air75hvac.com/hvac-short-cycling/ IN PROGRESS: >* Speedy Garage Doors * US Garage Door Repair * Us Garage Repair * Premier Garage Repair * Crestln | 0 |  | 4814815610
10872733839 | Daily Performance | Update |  | Toula Elwell | 09/January/2026 03:42:05 PM | 1/9/2026 >* Fnished the Check All Addresses & Phone Numbers task * Finished the monthly task Ahrefs Crawls (Ran crawls on all websites for this month and have a separate task where I am working on and verifying issues) * Working on and am stuck on the Address Pages for All Subdomains task (I need you to create "Address Pages" for each of the Subdomains, in this case ignore the Main Websites. Basically make a new Page with that Subdomain Location's Address as the name, make sure to include: Address. Tagline. Phone Number. Business Description. 4 Images. 3 Provided Services. 2 Locations ( Outbound Links )- City- State- Social Media SHARE links- 4 Services ( Outbound Links )- Hours of operation- Contact Form ): A1 Chimney subdomains minus the ads subdomains STUCK AS I DON'T KNOW THE ADRESSES (https://co.a-1chimney.com/wp-admin/edit.php?post_type=page, https://det.a-1chimney.com/wp-admin/edit.php?post_type=page, https://ct-ads.a-1chimney.com/wp-admin/edit.php?post_type=page, https://co.a-1chimney.com/wp-admin/edit.php?post_type=page, https://dfw-ads.a-1chimney.com/wp-admin/edit.php?post_type=page, https://det.a-1chimney.com/wp-admin/edit.php?post_type=page, https://sac.a-1chimney.com/wp-admin/edit.php?post_type=page, https://de.a-1chimney.com/wp-admin/edit.php?post_type=page, https://ok.a-1chimney.com/wp-admin/edit.php?post_type=page) US GARAGE REPAIR DONE A1 GARAGE DOOR REPAIR DONE (https://ga.a-1garagedoorrepair.com/303-perimeter-center-north-322-atlanta-georgia-30346/, https://ct.a-1garagedoorrepair.com/20-summer-street-402-stamford-ct-06901/) SPEEDY GARAGE DOORS DONE (https://ct.speedygaragedoors.com/100-pearl-street-1458-hartford-ct-06103/, https://ma.speedygaragedoors.com/186-lincoln-st-106-boston-ma-02110/, https://pa.speedygaragedoors.com/100-pearl-street-1458-hartford-ct-06103/) PREMIER GARAGE REPAIR DONE (https://ct.premiergaragerepair.net/1000-lafayette-blvd-1108-bridgeport-ct-06604/, https://ma.premiergaragerepair.net/1500-district-ave-2052-burlington-ma-01803/, https://pa.premiergaragerepair.net/2-logan-sq-ste-382-philadelphia-pa-19103-2733/) CRESTLN DONE (https://oh.crestln.com/7055-engle-rd-148c-middleburg-heights-oh-44130/, https://il.crestln.com/15635-s-94th-ave-114c-orland-park-il-60462/, https://ct.crestln.com/386-main-st-409c-middletown-ct-06457/) CRESTLN IN PROGRESS (https://dc.crestln.com/wp-admin/post.php?post=3225&action=edit, https://nj.crestln.com/wp-admin/post.php?post=3790&action=edit, https://tx.crestln.com/wp-admin/post.php?post=3411&action=edit, https://ga.crestln.com/wp-admin/post.php?post=3318&action=edit, https://ma.crestln.com/wp-admin/post.php?post=2795&action=edit, https://md.crestln.com/wp-admin/post.php?post=3325&action=edit, https://va.crestln.com/wp-admin/post.php?post=3269&action=edit) >* Finished the weekly plugin update task on all websites and their slugs * Finished working on the weekly blog posts task for week 2 FINISHED ALL: >* A1 CHIMNEY - https://www.a-1chimney.com/blog/chimney-repair-article/ * A1 Garage Door Repair - https://www.a-1garagedoorrepair.com/garage-door-making-grinding-noise/ * Air 75 HVAC - https://www.air75hvac.com/hvac-short-cycling/ * Speedy Garage Doors - https://www.speedygaragedoors.com/garage-door-problems-homeowners-ignore/ * US Garage Door Repair - https://www.us-garagedoorrepair.com/garage-door-services-matter/ * Us Garage Repair - https://www.usgaragerepair.net/garage-door-services-matter/ * Premier Garage Repair - https://www.premiergaragerepair.net/garage-door-balance-issues/ * Crestln - https://www.crestln.com/roof-ventilation-problems/ | 0 |  | 4818065988
10872736541 | Passwords | Update |  | Jose Demasi | 30/December/2025 09:21:50 AM | Gmail: - Toula@a-1chimney.com - Toula#a1c! Siteground Ahrefs | 0 |  | 4785235034
10872789781 | Check All Addresses & Phone Numbers | Update |  | Jose Demasi | 30/December/2025 11:30:51 AM | Check all the Addresses and Phone Numbers on the Websites and Subdomains and compare them to the General Information Excel File on Drive to make sure they are correct. | 0 |  | 4785739845
10872789781 | Check All Addresses & Phone Numbers | Update |  | Toula Elwell | 02/January/2026 04:16:15 PM | Need energy builder group sitemap link as you deleted the link two days ago | 0 |  | 4792573578
10872789781 | Check All Addresses & Phone Numbers |  | Reply | Toula Elwell | 09/January/2026 02:49:18 PM | Jose mentioned we don't touch that one now | 0 |  | 4817880168 | 4792573578
10872793272 | Ahrefs Crawls | Update |  | Jose Demasi | 30/December/2025 11:55:19 AM | Run New Crawls on Ahrefs on Websites after making a significant number of changes to make sure there aren't any issues or broken links. | 0 |  | 4785812374
10872793272 | Ahrefs Crawls | Update |  | Toula Elwell | 09/January/2026 03:40:03 PM | Month 1 running crawls on all websites done | 0 |  | 4818059645
10873095677 | Website Basics | Update |  | Jose Demasi | 30/December/2025 10:03:04 AM | General Website Rules (Applicable to all Websites): 1. Business name must be separated with spaces "USGarageRepair" > "US Garage Repair" 2. Buttons needs to be not too big (padding: 50px ,15px) 3. Top button must be link to the company phone number 4. In our services section the aspect ratio of the images should be corrected and not cropped 5. Fix all links in the website to work and to have hover effect (in site settings) 6. All Images must be watermarked ! 7. Contact Us page must include a contact form 8. Blog page must include only the blog posts 9. Single post page must include a custom sidebar 10. Services and Posts content must be more organized with Headlines, text, lists, etc... 11. All websites should include the local SEO star rating at the footer, ( see existing websites for example ) | 0 |  | 4785420113
10873129020 | Check Mobile Responsiveness | Update |  | Jose Demasi | 30/December/2025 11:19:55 AM | Check Mobile Responsiveness on all Websites for any Issues - Check both on Personal Phone and on Memu Emulator | 0 |  | 4785703100
10873142273 | Migration Basics | Update |  | Jose Demasi | 30/December/2025 10:06:35 AM | Siteground - Create Subdomain Siteground - File Manager Create Migration Folder Create ZIP of Public_html with Website Name Move to Migration Folder Siteground - MYSQL Acesss PhpMyAdmin Export File into Desktop .sql Siteground - File Manager File Upload .sql on Migration Folder Move Both Files on Migration Folder to Subdomain Website Folder ( ex: ct.website ) Extract .zip move .zip back to migration folder Move New Public Html to Subdomain Website Folder Siteground - MYSQL Databases - Create Database Get - Name db7nac6tjsbbo0 Users - Create User - User uprxwnxnr6dqx - Password hde7qpzorrm5 Give Database Access to User for Subdomain Change Label to Subdomain name Import Database Dumb Choose .sql File on Subdomain Folder Siteground - File Manager Move .sql back to Migration Folder Open Public Html WP-CONFIG.PHP Change Name - User - Password Values to New Ones WP-Content / Plugins / Delete SG-Cachepress Siteground - Speed - CDN Basic Free Select Activate Free Siteground - Wordpress Add Existing Site Choose Subdomain Autoupdate Turn off Auto Update Plugins Siteground - File Manager Go to Public.html .htacess Delete from 1 to 10 - ( # END HTTPS ) Wordpress - Search and Replace www.web.net ct.web.net www.ct.web.net ct.web.net mo.a-1chimney.com Missouri MISSOURI (888) 839-9114 800 E 101st Terrace #347, Kansas City, MO 64131 , MO A1 Chimney - Kansas City Kansas City Kansas Siteground - Security Activate SSL for Subdomain Enforce HTTPS Siteground - Speed Open Caching Open Dynamic Cache Clean Both Open Memcached Clean | 0 |  | 4785435693
10873227767 | Design New Watermark for Air 75 | Update |  | Toula Elwell | 30/December/2025 10:55:51 AM | watermark is thumbnail | 0 |  | 4785601883
10873227767 | Design New Watermark for Air 75 | Update |  | Toula Elwell | 30/December/2025 01:48:27 PM |  | 0 | 2647547952 | 4786198463
10873227767 | Design New Watermark for Air 75 | Update |  | Toula Elwell | 30/December/2025 02:59:29 PM |  | 0 | 2647788445 | 4786463966
10873227767 | Design New Watermark for Air 75 | Update |  | Toula Elwell | 31/December/2025 11:58:03 AM |  | 0 | 2649251283 | 4788171532
10873227767 | Design New Watermark for Air 75 |  | Reply | Jose Demasi | 31/December/2025 12:01:35 PM | Remove Air 75 duplicate name Do 2 Watermarks, one for service, one for blogs less quare remove middle section lower bottom bar | 0 |  | 4788179242 | 4788171532
10873227767 | Design New Watermark for Air 75 |  | Reply | Toula Elwell | 31/December/2025 12:11:50 PM | @Jose Demasi All Done | 0 |  | 4788199328 | 4788171532
10873227767 | Design New Watermark for Air 75 | Update |  | Toula Elwell | 31/December/2025 12:11:40 PM |  | 0 | 2649279439,2649279441 | 4788199082
10873227767 | Design New Watermark for Air 75 | Update |  | Toula Elwell | 31/December/2025 12:14:26 PM |  | 0 | 2649283054,2649283055 | 4788204659
10873227767 | Design New Watermark for Air 75 | Update |  | Toula Elwell | 31/December/2025 12:23:45 PM |  | 1 | 2649297570,2649297573 | 4788232157
10873227767 | Design New Watermark for Air 75 |  | Reply | Jose Demasi | 31/December/2025 12:24:37 PM | 👍 | 0 |  | 4788233610 | 4788232157
10873227767 | Design New Watermark for Air 75 | Update |  | Toula Elwell | 31/December/2025 12:30:06 PM | Blue Color now matches | 0 | 2649310790,2649310793 | 4788252487
10873851197 | Ahrefs Setup | Update |  | Jose Demasi | 30/December/2025 11:06:49 AM | Create an Account on Ahrefs - Add All the Website for Analytics - Add Meta Tag to Homepage to Verify - Run Crawls and Verify Issues | 0 |  | 4785665964
10873851197 | Ahrefs Setup | Update |  | Toula Elwell | 05/January/2026 10:53:50 AM | What do you mean by verify issues? | 1 |  | 4798670808
10873851197 | Ahrefs Setup |  | Reply | Toula Elwell | 09/January/2026 02:50:38 PM | Jose mentioned it means solve but to ignore the a1chimney ones for now | 0 |  | 4817885048 | 4798670808
10874099361 | Training Videos | Update |  | Jose Demasi | 30/December/2025 11:30:07 AM | I've added Training Videos on Drive for Website Basic Building and Formatting, Watch whenever you have the time. | 0 |  | 4785737455
10874158984 | Create Address Pages for All Subdomains | Update |  | Jose Demasi | 30/December/2025 11:34:26 AM | I need you to create "Address Pages" for each of the Subdomains, in this case ignore the Main Websites. Basically make a new Page with that Subdomain Location's Address as the name, make sure to include: Address Tagline Phone Number Business Description 4 Images 3 Provided Services 2 Locations ( Outbound Links ) - City - State - Social Media SHARE links - 4 Services ( Outbound Links ) - Hours of operation - Contact Form Examples: - https://kci.a-1chimney.com/3100-47th-ave-378-long-island-city-ny-11101/ https://ct.usgaragerepair.net/100-pearl-st-1443-hartford-ct-06103/ | 0 |  | 4785749183
10874158984 | Create Address Pages for All Subdomains | Update |  | Toula Elwell | 06/January/2026 03:27:58 PM | A1 Chimney subdomains minus the ads subdomains STUCK AS I DON'T KNOW THE ADRESSES (https://co.a-1chimney.com/wp-admin/edit.php?post_type=page, https://det.a-1chimney.com/wp-admin/edit.php?post_type=page, https://ct-ads.a-1chimney.com/wp-admin/edit.php?post_type=page, https://co.a-1chimney.com/wp-admin/edit.php?post_type=page, https://dfw-ads.a-1chimney.com/wp-admin/edit.php?post_type=page, https://det.a-1chimney.com/wp-admin/edit.php?post_type=page, https://sac.a-1chimney.com/wp-admin/edit.php?post_type=page, https://de.a-1chimney.com/wp-admin/edit.php?post_type=page, https://ok.a-1chimney.com/wp-admin/edit.php?post_type=page ) | 0 | 2661631223 | 4805638515
10874158984 | Create Address Pages for All Subdomains |  | Reply | Toula Elwell | 09/January/2026 02:51:10 PM | Jose will look into it and mentioned to leave the task as stuck till I can complete the ticket | 0 |  | 4817886791 | 4805638515
10874242244 | Website Users | Update |  | Jose Demasi | 30/December/2025 11:44:11 AM | When creating a new Website Make sure to create the following Users for Template Integration - Privacy - Single City - Single Location - Single Post - Single Service - A1Tools | 0 |  | 4785775186
10874280035 | Website Plugins | Update |  | Jose Demasi | 31/December/2025 09:21:19 AM | When creating a new Website make sure to Install the Following Plugins - Elementor - Elementor Pro ( Drive ) - Meta Tag Manager - Security Optimizer - Speed Optimizer - Wp All Import Pro ( Drive ) - Wp All Import Yoast Add-On ( Drive ) - Yoast SEO - Yoast SEO Premium ( Drive ) | 0 |  | 4787799452
10874346173 | SEO Score Improvement | Update |  | Jose Demasi | 30/December/2025 11:57:30 AM | Work on Improving the SEO for all Websites and Subdomains by checking their Status on Yoast. Priority Levels - Red - Orange - Green Ignore Blue and Gray | 0 |  | 4785819676
10874394576 | Readibility Score Improvement | Update |  | Jose Demasi | 30/December/2025 11:59:58 AM | Improve the Readability Score on all Pages and Blogs, this is directly tied to the Keywords used in SEO. | 0 |  | 4785829375
10874426145 | A1 Chimney Website - Our Team | Update |  | Jose Demasi | 30/December/2025 12:05:47 PM | Make Changes to the Our Team Page on A1 Chimney Main Page and Subdomains - Add Toula as Web Developer ( Ask Eve to take your Photo and send it to Rodrigo for Photoshop ) - Remove Eli Deblinger - Remove Bianca | 0 |  | 4785863300
10874495923 | Drive Folder Buildup | Update |  | Jose Demasi | 30/December/2025 12:17:00 PM | Build up the Drive Folder with the Logos of Every Website as well as their Watermark Photoshop Files for Future use. Drive - Websites - Name of Website - Logo Drive - Websites - Name of Website - Watermark Make Logo Variations - Grayscale - Inverted Colors - Full White - Full Black Remake Missing Watermarks | 0 |  | 4785904807
10874495923 | Drive Folder Buildup | Update |  | Toula Elwell | 06/January/2026 02:21:42 PM | I don't have link to emergency plumbing corp in sitegrounds so I can't fill out drive websites emergency plumbing corp section; but I will continue to fill out the others | 1 |  | 4805260612
10874495923 | Drive Folder Buildup |  | Reply | Toula Elwell | 09/January/2026 02:51:32 PM | Jose mentioned he will get me access | 0 |  | 4817887940 | 4805260612
10874495923 | Drive Folder Buildup | Update |  | Toula Elwell | 06/January/2026 02:37:56 PM | Stuck on top up roofing as i have no siteground link for that one too | 1 |  | 4805341017
10874495923 | Drive Folder Buildup |  | Reply | Toula Elwell | 09/January/2026 02:51:35 PM | Jose mentioned he will get me access | 0 |  | 4817888090 | 4805341017
10874530608 | Everdoors Website Design | Update |  | Jose Demasi | 30/December/2025 12:13:04 PM | Prepare Design ideas for New Website Company Name : Everdoors ( Garage Door Company ) | 0 |  | 4785890151
10874644946 | Website Familiarity | Update |  | Jose Demasi | 30/December/2025 12:28:30 PM | Get acquainted with our existing websites by exploring them and checking out the layout and design styles, you may also want to check other companies websites for ideas. | 0 |  | 4785933710
10874716553 | Plugin Update | Update |  | Jose Demasi | 30/December/2025 12:35:53 PM | Make sure the Plugins are up to Date on Every Website ( Do not enable Auto-Updates ) | 0 |  | 4785961737
10874716553 | Plugin Update | Update |  | Toula Elwell | 02/January/2026 10:57:34 AM | Week 1 Done | 0 |  | 4791330701
10874716553 | Plugin Update | Update |  | Toula Elwell | 08/January/2026 03:13:28 PM | week 2 done | 0 |  | 4814425114
10880462173 | Fix Incorrect Address - Crestline MD | Update |  | Jose Demasi | 31/December/2025 09:08:09 AM | Fix the Address on Crestline - MD Subdomain Current Address is 4701 Sangamore Rd #152C, Bethesda, MD 20816 Correct Address is without the C 4701 Sangamore Rd #152, Bethesda, MD 20816 | 0 |  | 4787777668
10880462173 | Fix Incorrect Address - Crestline MD | Update |  | Toula Elwell | 31/December/2025 09:32:50 AM |  | 1 | 2648975912 | 4787819319
10880462173 | Fix Incorrect Address - Crestline MD |  | Reply | Jose Demasi | 31/December/2025 09:35:32 AM | 👍 Remember to also clean the cache | 0 |  | 4787822892 | 4787819319
10880462173 | Fix Incorrect Address - Crestline MD |  | Reply | Toula Elwell | 31/December/2025 09:36:49 AM | @Jose Demasi That sounds great I just flushed it!! Thank you for reminding me | 0 |  | 4787824543 | 4787819319
10880789410 | Crestline Subdomains - Check Mobile Responsiveness and Fix | Update |  | Jose Demasi | 31/December/2025 09:53:01 AM | There's a few mistakes in the mobile view, specially in the subdomains on the homepage, fix it whenever possible. | 0 | 2649005861,2649007895 | 4787872751
10880789410 | Crestline Subdomains - Check Mobile Responsiveness and Fix | Update |  | Toula Elwell | 05/January/2026 04:41:39 PM | Figured out fix | 0 | 2658305668 | 4800789482
10881895214 | Use new watermarks in Air 75, replace all existing ones | Update |  | Toula Elwell | 02/January/2026 02:39:32 PM | I don't know how to change the pop up widgets image | 0 |  | 4792296315
10910325973 | Configure websites in a1 tools | Update |  | Toula Elwell | 05/January/2026 11:51:40 AM | Add user in wordpress and add site and their slugs to a1 tools | 0 |  | 4799081208
10914723755 | Crestline Subdomains - Fix errors found on subdomains homepage | Update |  | Toula Elwell | 05/January/2026 04:23:01 PM | Found this on subdomain but not main page: | 0 | 2658250822 | 4800709468
10914723755 | Crestline Subdomains - Fix errors found on subdomains homepage | Update |  | Toula Elwell | 05/January/2026 04:26:19 PM | Found Fix | 0 | 2658262348 | 4800720649
10980193187 | Remove Air 75 License from Website | Update |  | Jose Demasi | 12/January/2026 03:10:02 PM | Please remove the AIR75 License Number, check header, footer and templates. as it may be present in several pages. | 0 | 2675847337 | 4823199429